## Slide 1: Bi-Weekly Cadence Commitment Template Past 14 days
No. | Action | Action Party | Threat | Due Date | Status
10-4.1 |  |  |  |  | New
10-4.2 |  |  |  |  | New
10-4.3 |  |  |  |  | 
10-4.4 |  |  |  |  | 
10-4.5 |  |  |  |  | 
10-4.6 |  |  |  |  | 
10-4.7 |  |  |  |  | 
10-4.8 |  |  |  |  | 
10-4.9 |  |  |  |  | 
10-4.10 |  |  |  |  | 
10-4.11 |  |  |  |  | 
10-4.12 |  |  |  |  | 
10-4.13 |  |  |  |  | 
10-4.14 |  |  |  |  | 
10-4.15 |  |  |  |  | 
10-4.16 |  |  |  |  | 
On track
At risk
Delayed
Completed
New

## Slide 2: Bi-Weekly Cadence Commitment Template Next 14days
No. | Action | Action Party | Threat | Due Date | Status
10-4.1 |  |  |  |  | New
10-4.2 |  |  |  |  | New
10-4.3 |  |  |  |  | 
10-4.4 |  |  |  |  | 
10-4.5 |  |  |  |  | 
10-4.6 |  |  |  |  | 
10-4.7 |  |  |  |  | 
10-4.8 |  |  |  |  | 
10-4.9 |  |  |  |  | 
10-4.10 |  |  |  |  | 
10-4.11 |  |  |  |  | 
10-4.12 |  |  |  |  | 
10-4.13 |  |  |  |  | 
10-4.14 |  |  |  |  | 
10-4.15 |  |  |  |  | 
10-4.16 |  |  |  |  | 
On track
At risk
Delayed
Completed
New

## Slide 3: Bi-Weekly Cadence Commitment Template
No. | Action | Owner | Due Date | Status
10-4.1 | Follow up with the business on Magnolia migration issues | Brett | 10/14/2013 | Completed
10-4.2 | Set up time with Ethel to update POAP to include Mar 2013 onwards | Simar | 10/14/2013 | Delayed
10-4.3 | Set up time with Ethel to get budget information and “value delivered” included on POAP | Lucy | 10/14/2013 | Delayed
10-4.4 | Develop what UA will come to the table with as far as PMO deliverables and present them to the Global team | Lucy | 10/31/2013 | On Track
10-4.5 | Align current deliverables with PMO dashboard (e.g. governance, business case, etc.) | Lucy | 10/10/2013 | Completed
10-4.6 | Add link to migration schedule to dashboard | Vinit | 10/10/2013 | Completed
10-4.7 | Adjust dashboard to align with UA perspective on status | Sylvia | 10/10/2013 | Completed
10-4.8 | Update status dashboard to have noun, no verbs in deliverables | Deborah | 10/10/2013 | Completed
10-4.9 | Add deliverables to dashboard for Canadian satellite and cancellation of Brazil | Dwayne | 10/10/2013 | Completed
10-4.10 | Provide Deborah a revised migration size for representation on dashboard | Vinit | 10/10/2013 | Completed
10-4.11 | Ensure all team members include their vacation schedule on calendar for approval | All | 10/18/2013 | On Track
10-4.12 | Provide vacation schedule to Ethel for approval | Simar | 10/18/2013 | On Track
10-4.13 | Add issues, risks & RTG on migration dashboard | Deborah | 10/10/2013 | Completed
10-4.14 | Identify backfill for Sylvia while she is away | Deborah | 10/10/2013 | Completed
10-4.15 | Provide Ethel with IMBA’s responsibilities related to metadata work | Deborah | 10/18/2013 | On Track
10-4.16 | Engage BLs to identify attendees to NOLA and Houston Roadshows | Connie | 10/11/2013 | Completed
On track
At risk
Delayed
Completed
New
EXAMPLE

## Slide 4: Overall Project Plan
 | 2013 { $2.881(Budget) / $2.815(Actuals and Total Expected Charges for the remainder of the year) } |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  | 
Work Streams | Mar |  | Apr |  | May |  | Jun |  | Jul |  | Aug |  | Sep |  | Oct |  | Nov |  | Dec |  | J | F | M | A | M | J | J | A | S | O | N | D | Jan – Dec |  |  | 
Actual / LE | - |  | - |  | $53.6K |  | $229.9K |  | $171.8K |  | $245.5K |  | $481.3K |  | $708.2K |  | $488.8K |  | $436.1K |  | $40M |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Programme Management
Change Management
Information Architecture
&
Value
Migration
Key Milestone
Key Dependency
On Track
At Risk
Delayed
Completed

## Slide 5: Overall Project Plan
 | 2013 { $2.881(Budget) / $2.815(Actuals and Total Expected Charges for the remainder of the year) } |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |  |  | 
Work Streams | Mar |  | Apr |  | May |  | Jun |  | Jul |  | Aug |  | Sep |  | Oct |  | Nov |  | Dec |  | J | F | M | A | M | J | J | A | S | O | N | D | Jan – Dec |  |  | 
Actual / LE | - |  | - |  | $53.6K |  | $229.9K |  | $171.8K |  | $245.5K |  | $481.3K |  | $708.2K |  | $488.8K |  | $436.1K |  | $40M |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Programme Management
Change Management
Information Architecture
&
Value
Migration
Build & Maintain Integrated Work Plan
Integrated Work Plan for Mass Migration
UA Roadshow Development and Execution
Change Mgmt, Training Planning & Comms
Roadshow Launch
SP13 Change Plan
Organizational Alignment & Core Migration Training
Migration Schedule
Early Adopter Migration Schedule
Value Agenda
Change Impact Assessment
Architecture & Topology Diagrams
Pre Migration
GRM, Compliance, Exp. Controls Requirements
Metadata & Topology Development
Change Impact Assessment
Migration Manifests
Site Templates & Security Model
Early Adopter Migrations Complete
Reporting, Conditioning, & Migration (LL)
IICE POC Demo
IICE POC
Shared Folder Migration
Public Folders Migration
Remove LL access (Early Adopters)
Hypercare & Remediation - Early Adopters & Core Migrations
Hypercare Model - Core
Migration Start
Topology & Metadata – Early Adopters
TSI tool in place to generate target sites
SP07 Data Disposal Assessment
SP07 Data Disposal Assessment
Remove LL access by Collections
NOLA Site Visit
& Roadshow
Change Mgmt & Training
Plan – Core Migration
LOB Change Execution
Business Readiness Assessment
EA Change Toolkit R1
EA Change Toolkit R2
EA Toolkit Creation
Exploration & EA Training Plan
Organizational Alignment
Plan
Management Processes &Templates
PMO Handbook Release 1
PMO Handbook Release 2
PDF Deliverables Management
SG2
SG3
SG4
Metadata Req. Traceability Matrix
Hypercare Model - EA
EA Topology Diagram
Training Material
UAX & EA Training Plan
Global Inf. Compliance Comms
Key Milestone
Key Dependency
On Track
At Risk
Delayed
Completed
UA Logical Mappings (Value Agenda)
Reset & Kick-off
Early Adopter Migration Plan?
Set-up and Planning (2014+)
SP2007 to SP2010 Migration (Residuals)
SP10 Residuals Complete
Livelink Inventory Generation (started in 2012)
LL Inventory
UAD Equipment Condition History
Pilot
IICE POC Demo II
Ext Access (AMS)
Canadian Satellite (Base)
PCP & Project Charter
New SharePoint Site Provisioning
Brazil Satellite
EXAMPLE