## Slide 1: LOCATION PREPARATION PROCESS IMPROVEMENT PILOT IMPLEMENTATION
AGBADA-57 LOCATION
11th June 2013
SPDC – Port Harcourt

## Slide 2: Original Scope of Works
Mobilisation
Bush Clearing/Stripping
Earthworks (Sandfilling)
Waste Pit Construction
Cement Slab Construction
Generator Slab Construction
Chemical Slab Construction
Cement Stabilisation
Crushed granite rock base course
Hot-rolled asphalt surfacing
Perimeter Fence Construction

## Slide 3: Revised (LEAN) Scope of Works
Mobilisation/Demobilisation
Bush Clearing/Stripping
Earthworks (Sandfilling)
Waste Pit Construction (Reduced Size)
Installation of impermeable geotextile fabric (5,060m2)
Installation of Durabase Mats (5,060m2)
Crushed granite rock base course (3,800m2
Hot-rolled asphalt surfacing (3,800m2)
Perimeter Fence Construction

## Slide 4: Key Changes
Reduced Waste Pit
Elimination of Generator Slab
Elimination of Chemical Slab
Elimination of Cement Slab
Elimination of Cement Stabilisation and Crushed Rock Base Course
Elimination of Asphalt Surfacing

## Slide 5: Cost Savings
S/No. | Work Item | Cost Savings (F$)
1 | Base Preparation & Surfacing | 249,952.77
2 | Waste Pit | 102,786.11
3 | Generator Slab | 93,674.33
4 | Chemical Slab | 48,699.49
5 | Cement Slab | 17,877.68
6 | Use of logistics contract for the transportation of durabase mats | 59,394.17
 | Total Savings | 572,384.55

## Slide 6
Original Scope of Works | Revised (LEAN) Scope of Works
Mobilisation | Mobilisation/Demobilisation
Bush Clearing/Stripping | Bush Clearing/Stripping
Earthworks (Sandfilling) | Earthworks (Sand Filling)
Waste Pit Construction | Waste Pit Construction (Reduced Size)
Cement Slab Construction | Installation of impermeable geotextile fabric (5,060m2)
Generator Slab Construction | Installation of Durabase Mats (5,060m2)
Chemical Slab Construction | Crushed granite rock base course (3,800m2
Cement Stabilisation | Hot-rolled asphalt surfacing (3,800m2)
Crushed granite rock base course | Perimeter Fence Construction
Hot-rolled asphalt surfacing | 
Perimeter Fence Construction | 
Key Changes
Reduced Waste Pit Elimination of Generator Slab Elimination of Chemical Slab Elimination of Cement Slab Elimination of Cement Stabilisation and Crushed Rock Base Course Elimination of Asphalt Surfacing Haulage by Shell Transport against contractor