## Sheet1
|  |  | Land Clamping |  |  |  | Swamp Clamping |  |  |  | Sectional Replacement (Swamp)
| Activity | Department/Function | Original Entry | Minutes | Hours | Workdays (8hrs) | Original Entry | Minutes | Hours | Workdays (8hrs) | Original Entry | Minutes | Hours | Workdays (8hrs) | Comments
Notification/Confirmation | Observe leak and report | Leak Notifier
| Conduct overfly or ground visit | ROW
| Notify asset to shut in | MTC | 10 mins | 10 | 0.16667 | 0.020833 | 10 mins | 10 | 0.16667 | 0.020833 | 10 mins | 10 | 0.16667 | 0.020833
| Fountain Report | ROW
| Shut in identified stations | PMC | 8hrs | 480 | 8 | 1 | 5hrs | 300 | 5 |  | 8hrs | 480 | 8 | 1
| Pre-JIV/Repair Meeting (Security, HSE, Geomatics and others) | MTC | 30 mins | 30 | 0.5 | 0.0625 | 30 mins | 30 | 0.5 | 0.0625 | 30 mins | 30 | 0.5 | 0.0625
| Raise notification to all Regulators and advice JIV date | HSE | 60 mins | 60 | 1 | 0.125 | 60-120 mins | 120 | 2 | 0.25 |  | 0 | 0 | 0
| Notify CRO to process FTO | MTC | 10 mins | 10 | 0.16667 | 0.020833 | 10 mins | 10 | 0.16667 | 0.020833 | 10 mins | 10 | 0.16667 | 0.020833
| SAP Notification | MTC | 30 mins | 30 | 0.5 | 0.0625 | 30 mins | 30 | 0.5 | 0.0625 | 30 mins | 30 | 0.5 | 0.0625
| Prepare work packs (PO, Isolation work packs etc, premob.), work method and JHA & Obtain PTW from HSE | MTC | 71/2 hrs | 450 | 7.5 | 0.9375 | 71/2 hrs | 450 | 7.5 | 0.9375 | 71/2 hrs | 450 | 7.5 | 0.9375 | 1hr for WO &PO; Isolation is for operations; 6 hrs for Work method and JHA.; 30 mins to obtain PTW from HSE
TOTALS |  |  |  | 1070 | 17.8333 | 2.2292 |  | 950 | 15.8333 | 1.9792 |  | 1010 | 16.8333 | 2.1042
Isolation/ Containment | Confirmation of Security availabilty | OPS | 30 mins | 30 | 0.5 | 0.0625 | 24hrs | 1440 | 24 | 3 | 135 mins | 135 | 2.25 | 0.28125
| Confirmation of Logistics availabilty | OPS | 45 mins | 45 | 0.75 | 0.09375 | 60 mins | 60 | 1 | 0.125 | 45 mins | 45 | 0.75 | 0.09375
| PTW | OPS | 110 mins | 110 | 1.8333 | 0.22917 | 110 mins | 110 | 1.8333 | 0.22917 | 110 mins | 110 | 1.8333 | 0.22917
| Mobilise to site and carry out isolation/ switching | OPS | 240 mins | 240 | 4 | 0.5 | 240 mins | 240 | 4 | 0.5 | 240 mins | 240 | 0.5 | 0.5 | Depending on the location
| Confirm shutdown | OPS | 30 mins | 30 | 0.5 | 0.0625 | 30 mins | 30 | 0.5 | 0.0625 | 30 mins | 30 | 0.5 | 0.0625
| Notify completion of Isolation | OPS | 45 mins | 45 | 0.75 | 0.09375 | 45 mins | 45 | 0.75 | 0.09375 | 45 mins | 45 | 0.75 | 0.09375 | Due to poor network mostly, it takes an average of 45 minutes to receive confirmation of completed isolations.
| Confirmation of Security availabilty for containment | OSRT | 24Hrs | 1440 | 24 | 3 | 24Hrs | 1440 | 24 | 3 | 24Hrs | 1440 | 24 | 3
| Confirmation of Logistics availabilty for containment | OSRT | 2Hrs | 120 | 2 | 0.25 | 2Hrs | 120 | 2 | 0.25 | 2Hrs | 120 | 2 | 0.25
| Mobilise to site for first line response | OSRT | 48hrs | 2880 | 48 | 6 | 48hrs | 2880 | 48 | 6 | 48hrs | 2880 | 48 | 6
TOTALS |  |  |  | 4940 | 82.3333 | 10.2917 |  | 6365 | 106.0833 | 13.2604 |  | 5045 | 80.5833 | 10.5104
JIV Preparation/FTO Collection | Conduct contractor selection and approval | MTC | 10 mins | 10 | 0.16667 | 0.020833 | 10 mins | 10 | 0.16667 | 0.020833 | 10 mins | 10 | 0.16667 | 0.020833
| Conduct contractor selection and approval | OSRT | 5mins | 5 | 0.083333 | 0.010417 | 5 | 5 | 0.083333 | 0.010417 | 5 mins | 5 | 0.083333 | 0.010417
| Provide entry requirements for FTO elements | CIC/CRC | 3days | 1440 | 24 | 3 | 3days | 1440 | 24 | 3 | 3days | 1440 | 24 | 3
| Review work site security plan and obtain approvals | ASA | 48hrs | 2880 | 48 | 6 | 2days | 960 | 16 | 2 | 2days | 960 | 16 | 2
TOTALS |  |  |  | 4335 | 72.25 | 9.0312 |  | 2415 | 40.25 | 5.0312 |  | 2415 | 40.25 | 5.0312
PTW/Security Clearance | Prepare work method and JHA | Contractor | Over 6 hrs | 360 | 6 | 0.75 | 48 hrs | 2880 | 48 | 6 | 48 hrs | 2880 | 48 | 6
| Request PTW from HSE and provide required documentation | MTC | It took over 6 hrs to get the documentations from the contractor and upon approval 5 mins to request PTW | 360 | 6 | 0.75 | 3hrs | 180 | 3 | 0.375 | 3hrs | 180 | 3 | 0.375
| Arrange for transport | MTC | 2 hrs | 120 | 2 | 0.25 | 2hrs | 120 | 2 | 0.25 | 2hrs | 120 | 2 | 0.25
| Receive notification for security cover Provide security cover give final clearance for site mobilisation | MTC | 24hrs | 1440 | 24 | 3 | 48hrs | 2880 | 48 | 6 | 48hrs | 2880 | 48 | 6
| Review request in line with PTW checklist | Security | 2days | 960 | 16 | 2 | 2days | 960 | 16 | 2 | 2days | 960 | 16 | 2
| Issue PTW to PEPM | HSE | 05 min -30 min | 30 | 0.5 | 0.0625 | 05 -60 mins | 60 | 1 | 0.125 |  |  | 0 | 0
| Assign driver and vehicle | Journey Manager | 24hrs | 1440 | 24 | 3 | 24hrs | 1440 | 24 | 3 | 24hrs | 1440 | 24 | 3
| Collect required materials from PEPM | Journey Manager | 1day | 480 | 8 | 1 | 1day | 480 | 8 | 1 | 1day | 480 | 8 | 1
TOTALS |  |  |  | 5190 | 86.5 | 10.8125 |  | 9000 | 150 | 18.75 |  | 8940 | 149 | 18.625
Mobilisation/JIV Execution | Mobilise to site | Contractor | 4 hrs | 240 | 4 | 0.5 | 96 hrs | 5760 | 96 | 12 | 96 hrs | 5760 | 96 | 12
| Confirmation of Security availabilty | MTC | 24 hrs | 1440 | 24 | 3 | 24 hrs | 1440 | 24 | 3 | 24 hrs | 1440 | 24 | 3
| Confirmation of Logistics availabilty | MTC | 24hrs | 1440 | 24 | 3 | 24 hrs | 1440 | 24 | 3 | 24 hrs | 1440 | 24 | 3
| Confirm Fire Team's availability | MTC | 2 hrs | 120 | 2 | 0.25 | 2 hrs | 120 | 2 | 0.25 | 2 hrs | 120 | 2 | 0.25
| Confirm Regulator's Team's availability | MTC | 24 hrs | 1440 | 24 | 3 | 24hr | 1440 | 24 | 3 | 24Hrs | 1440 | 24 | 3
| Mobilise to site | MTC | 24 hrs | 1440 | 24 | 3 | 48 hrs | 2880 | 48 | 6 | 72 hrs | 4320 | 72 | 9
| Carry out JIV & Generate JIV Report and Preliminary Map | JIV Team - Includes OSRT, HSE, Community Relations, Governance, Geomatics, Regulators, ROW, etc. | 48hrs | 2880 | 48 | 6 | 24hrs | 1440 | 24 | 3 | 24Hrs | 1440 | 24 | 9
| Update incident in Fountain | MTC | 1 hr | 60 | 1 | 0.125 | 1 hr | 60 | 1 | 0.125 | 1hr | 60 | 1 | 0.125
TOTALS |  |  |  | 9060 | 151 | 18.875 |  | 14520 | 242 | 30.25 |  | 16020 | 267 | 33.375
Site Execution/Close Out | Site PREP- Build Cofferdam | MTC | 6hrs | 360 | 6 | 0.75 | 5days | 2400 | 40 | 5 | 5days | 2400 | 40 | 5
| Carry out site execution (clamping, sectional replacement). | MTC | 36 hrs | 2160 | 36 | 4.5 | 72 hrs | 4320 | 72 | 9 | 96 hrs | 5760 | 96 | 12
| Submit JIV report to Remediation Governance Team | MTC | [12 empty] | OSRT-Governance team action
| Submit JIV report to DCC | MTC | [12 empty] | OSRT-Governance team action
| Finalize all SAP issues including VOWD, SE and TECO | MTC | 1 hr | 60 | 1 | 0.125 | I hr | 60 | 1 | 0.125 | I hr | 60 |  | 0.125
TOTALS |  |  |  | 2520 | 42 | 5.25 |  | 6720 | 112 | 14 |  | 8160 | 136 | 17
|  |  | Land Clamping |  |  | Swamp Clamping |  |  | Sectional Replacement (Swamp)
|  | Activity | Minutes | Hours | Workdays (8hrs) | Minutes | Hours | Workdays (8hrs) | Minutes | Hours | Workdays (8hrs)
|  | Notification/Confirmation | 1070 | 17.8333 | 2.2292 | 950 | 15.8333 | 1.9792 | 1010 | 16.8333 | 2.1042
|  | Isolation/Containment | 4940 | 82.3333 | 10.2917 | 6365 | 106.0833 | 13.2604 | 5045 | 84.0833 | 10.5104
|  | JIV Preparation/FTO Collection | 4335 | 72.25 | 9.0312 | 2415 | 40.25 | 5.0312 | 2415 | 40.25 | 5.0312
|  | PTW/Security Clearance | 5190 | 86.5 | 10.8125 | 9000 | 150 | 18.75 | 8940 | 149 | 18.625
|  | Mobilisation/JIV Execution | 9060 | 151 | 18.875 | 14520 | 242 | 30.25 | 16020 | 267 | 33.375
|  | Site Execution/Close Out | 2520 | 42 | 5.25 | 6720 | 112 | 14 | 8160 | 136 | 17
|  | Totals |  |  | 56.4896 |  |  | 83.2708 |  |  | 86.6458

## Sheet2
| Activity | Hours | Hours | Hours | Workdays (8hrs) | Workdays (8hrs) | Workdays (8hrs)
Notification/Confirmation | Observe leak and report
Conduct overfly or ground visit
| Notify asset to shut in | 0.16667 | 0.16667 | 0.16667 | 0.020833 | 0.020833 | 0.020833
Fountain Report
| Shut in identified stations | 8 | 5 | 8 | 1 |  | 1
| Pre-JIV/Repair Meeting (Security, HSE, Geomatics and others) | 0.5 | 0.5 | 0.5 | 0.0625 | 0.0625 | 0.0625
| Raise notification to all Regulators and advice JIV date | 1 | 2 | 0 | 0.125 | 0.25 | 0
| Notify CRO to process FTO | 0.16667 | 0.16667 | 0.16667 | 0.020833 | 0.020833 | 0.020833
| SAP Notification | 0.5 | 0.5 | 0.5 | 0.0625 | 0.0625 | 0.0625
| Prepare work packs (PO, Isolation work packs etc, premob.), work method and JHA & Obtain PTW from HSE | 7.5 | 7.5 | 7.5 | 0.9375 | 0.9375 | 0.9375
TOTALS |  |  |  |  | 2.2292 | 1.9792 | 2.1042
Isolation/ Containment | Confirmation of Security availabilty | 0.5 | 24 | 2.25 | 0.0625 | 3 | 0.28125
| Confirmation of Logistics availabilty | 0.75 | 1 | 0.75 | 0.09375 | 0.125 | 0.09375
| PTW | 1.8333 | 1.8333 | 1.8333 | 0.22917 | 0.22917 | 0.22917
| Mobilise to site and carry out isolation/ switching | 4 | 4 | 0.5 | 0.5 | 0.5 | 0.5
| Confirm shutdown | 0.5 | 0.5 | 0.5 | 0.0625 | 0.0625 | 0.0625
| Notify completion of Isolation | 0.75 | 0.75 | 0.75 | 0.09375 | 0.09375 | 0.09375
| Confirmation of Security availabilty for containment | 24 | 24 | 24 | 3 | 3 | 3
| Confirmation of Logistics availabilty for containment | 2 | 2 | 2 | 0.25 | 0.25 | 0.25
| Mobilise to site for first line response | 48 | 48 | 48 | 6 | 6 | 6
TOTALS |  |  |  |  | 10.2917 | 13.2604 | 10.5104
JIV Preparation/FTO Collection | Conduct contractor selection and approval | 0.16667 | 0.16667 | 0.16667 | 0.020833 | 0.020833 | 0.020833
| Conduct contractor selection and approval | 0.083333 | 0.083333 | 0.083333 | 0.010417 | 0.010417 | 0.010417
| Provide entry requirements for FTO elements | 24 | 24 | 24 | 3 | 3 | 3
| Review work site security plan and obtain approvals | 48 | 16 | 16 | 6 | 2 | 2
TOTALS |  |  |  |  | 9.0312 | 5.0312 | 5.0312
PTW/Security Clearance | Prepare work method and JHA | 6 | 48 | 48 | 0.75 | 6 | 6
| Request PTW from HSE and provide required documentation | 6 | 3 | 3 | 0.75 | 0.375 | 0.375
| Arrange for transport | 2 | 2 | 2 | 0.25 | 0.25 | 0.25
| Receive notification for security cover Provide security cover give final clearance for site mobilisation | 24 | 48 | 48 | 3 | 6 | 6
| Review request in line with PTW checklist | 16 | 16 | 16 | 2 | 2 | 2
| Issue PTW to PEPM | 0.5 | 1 | 0 | 0.0625 | 0.125 | 0
| Assign driver and vehicle | 24 | 24 | 24 | 3 | 3 | 3
| Collect required materials from PEPM | 8 | 8 | 8 | 1 | 1 | 1
TOTALS |  |  |  |  | 10.8125 | 18.75 | 18.625
Mobilisation/JIV Execution | Mobilise to site | 4 | 96 | 96 | 0.5 | 12 | 12
| Confirmation of Security availabilty | 24 | 24 | 24 | 3 | 3 | 3
| Confirmation of Logistics availabilty | 24 | 24 | 24 | 3 | 3 | 3
| Confirm Fire Team's availability | 2 | 2 | 2 | 0.25 | 0.25 | 0.25
| Confirm Regulator's Team's availability | 24 | 24 | 24 | 3 | 3 | 3
| Mobilise to site | 24 | 48 | 72 | 3 | 6 | 9
| Carry out JIV & Generate JIV Report and Preliminary Map | 48 | 24 | 24 | 6 | 3 | 9
| Update incident in Fountain | 1 | 1 | 1 | 0.125 | 0.125 | 0.125
TOTALS |  |  |  |  | 18.875 | 30.25 | 33.375
Site Execution/Close Out | Site PREP- Build Cofferdam | 6 | 40 | 40 | 0.75 | 5 | 5
| Carry out site execution (clamping, sectional replacement). | 36 | 72 | 96 | 4.5 | 9 | 12
Submit JIV report to Remediation Governance Team
Submit JIV report to DCC
| Finalize all SAP issues including VOWD, SE and TECO | 1 | 1 |  | 0.125 | 0.125 | 0.125
TOTALS |  |  |  |  | 5.25 | 14 | 17

## Sheet3
DATA ANALYSIS - PIPELINES IMPROVEMENT PROJECT (DEEP DIVE)
|  | CLAMPING |  | SECT REPLACEMENT
| Activity | LAND (Hrs) | SWAMP (Hrs) | SWAMP (Hrs)
Notification/Confirmation | Observe leak and report
Conduct overfly or ground visit
Notify asset to shut in
Fountain Report
| Shut in identified stations | ¦¦¦¦¦¦¦¦ | ¦¦¦¦¦ | ¦¦¦¦¦¦¦¦
Pre-JIV/Repair Meeting (Security, HSE, Geomatics and others)
| Raise notification to all Regulators and advice JIV date | ¦ | ¦¦
Notify CRO to process FTO
SAP Notification
| Prepare work packs (PO, Isolation work packs etc, premob.), work method and JHA & Obtain PTW from HSE | ¦¦¦¦¦¦¦ | ¦¦¦¦¦ | ¦¦¦¦¦¦¦¦
Isolation/ Containment | Confirmation of Security availabilty |  | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦
| Confirmation of Logistics availabilty |  | ¦
| PTW | ¦ | ¦ | ¦
| Mobilise to site and carry out isolation/ switching | ¦¦¦¦ | ¦¦¦¦
Confirm shutdown
Notify completion of Isolation
| Confirmation of Security availabilty for containment | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦
| Confirmation of Logistics availabilty for containment | ¦¦ | ¦¦ | ¦¦
| Mobilise to site for first line response | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦
JIV Preparation/FTO Collection | Conduct contractor selection and approval
Conduct contractor selection and approval
| Provide entry requirements for FTO elements | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦
| Review work site security plan and obtain approvals | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦
PTW/Security Clearance | Prepare work method and JHA | ¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦
| Request PTW from HSE and provide required documentation | ¦¦¦¦¦¦ | ¦¦¦ | ¦¦¦
| Arrange for transport | ¦¦ | ¦¦ | ¦¦
| Receive notification for security cover Provide security cover give final clearance for site mobilisation | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦
| Review request in line with PTW checklist | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦
| Issue PTW to PEPM |  | ¦
| Assign driver and vehicle | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦
| Collect required materials from PEPM | ¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦
Mobilisation/JIV Execution | Mobilise to site | ¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦
| Confirmation of Security availabilty | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦
| Confirmation of Logistics availabilty | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦
| Confirm Fire Team's availability | ¦¦ | ¦¦ | ¦¦
| Confirm Regulator's Team's availability | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦
| Mobilise to site | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦
| Carry out JIV & Generate JIV Report and Preliminary Map | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦
| Update incident in Fountain | ¦ | ¦ | ¦
Site Execution/Close Out | Site PREP- Build Cofferdam | ¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦
| Carry out site execution (clamping, sectional replacement). | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦
Submit JIV report to Remediation Governance Team
Submit JIV report to DCC
| Finalize all SAP issues including VOWD, SE and TECO | ¦
Hours

## LandPareto
Activity | Land (Workdays) | Percent of Total | Cum %
Mobilisation/JIV Execution | 18.875 | 33.41% | 33.41%
PTW/Security Clearance | 10.8125 | 19.14% | 52.55%
Isolation/Containment | 10.2917 | 18.22% | 70.77%
JIV Preparation/FTO Collection | 9.0312 | 15.99% | 86.76%
Site Execution/Close Out | 5.25 | 9.294% | 96.05%
Notification/Confirmation | 2.2292 | 3.946% | 100%

## SwampPareto
Activity | Swamp (Workdays) | Percent of Total | Cum %
Mobilisation/JIV Execution | 30.25 | 36.33% | 36.33%
PTW/Security Clearance | 18.75 | 22.52% | 58.84%
Site Execution/Close Out | 14 | 16.81% | 75.66%
Isolation/Containment | 13.2604 | 15.92% | 91.58%
JIV Preparation/FTO Collection | 5.0312 | 6.042% | 97.62%
Notification/Confirmation | 1.9792 | 2.377% | 100%

## SectReplPareto
Activity | Sect Repl. (Workdays) | Percent of Total | Cum %
Mobilisation/JIV Execution | 33.375 | 38.52% | 38.52%
PTW/Security Clearance | 18.625 | 21.5% | 60.01%
Site Execution/Close Out | 17 | 19.62% | 79.63%
Isolation/Containment | 10.5104 | 12.13% | 91.76%
JIV Preparation/FTO Collection | 5.0312 | 5.807% | 97.57%
Notification/Confirmation | 2.1042 | 2.428% | 100%

## HistData (hidden)
Land (Workdays) | Swamp (Workdays) | Sect Repl. (Workdays) | #REF! |  | Bins | Land (Workdays)Freq | Swamp (Workdays)Freq | Sect Repl. (Workdays)Freq
2.2292 | 1.9792 | 2.1042 |  | 33.375 | 4 | 1 | 1 | 1 | 1.9792 | (0.5, 4)
10.2917 | 13.2604 | 10.5104 |  | 1.9792 | 7.5 | 1 | 1 | 1 | 5.75 | (4, 7.5)
9.0312 | 5.0312 | 5.0312 | Bins | 10 | 11 | 3 | 0 | 1 | 9.25 | (7.5, 11)
10.8125 | 18.75 | 18.625 | Interval | 3.5 | 14.5 | 0 | 2 | 0 | 12.75 | (11, 14.5)
18.875 | 30.25 | 33.375 |  |  | 18 | 0 | 0 | 1 | 16.25 | (14.5, 18)
5.25 | 14 | 17 |  |  | 21.5 | 1 | 1 | 1 | 19.75 | (18, 21.5)
[5 empty] | 25 | 0 | 0 | 0 | 23.25 | (21.5, 25)
[5 empty] | 28.5 | 0 | 0 | 0 | 26.75 | (25, 28.5)
[5 empty] | 32 | 0 | 1 | 0 | 30.25 | (28.5, 32)
[5 empty] | 35.5 | 0 | 0 | 1 | 33.75 | (32, 35.5)

## Sheet4
Activity | Land (Workdays) | Swamp (Workdays) | Sect Repl. (Workdays)
Notification/Confirmation | 2.2292 | 1.9792 | 2.1042
Isolation/Containment | 10.2917 | 13.2604 | 10.5104
JIV Preparation/FTO Collection | 9.0312 | 5.0312 | 5.0312
PTW/Security Clearance | 10.8125 | 18.75 | 18.625
Mobilisation/JIV Execution | 18.875 | 30.25 | 33.375
Site Execution/Close Out | 5.25 | 14 | 17

## Sheet14
Activity | Land (Workdays) | Swamp (Workdays) | Sect Repl. (Workdays) |  | 33.375
Notification/Confirmation | 2.2292 | 1.9792 | 2.1042 | Notification/Confirmation | 0 | 6
Isolation/Containment | 10.2917 | 13.2604 | 10.5104 | Isolation/Containment | 0 | 5
JIV Preparation/FTO Collection | 9.0312 | 5.0312 | 5.0312 | JIV Preparation/FTO Collection | 0 | 4
PTW/Security Clearance | 10.8125 | 18.75 | 18.625 | PTW/Security Clearance | 0 | 3
Mobilisation/JIV Execution | 18.875 | 30.25 | 33.375 | Mobilisation/JIV Execution | 0 | 2
Site Execution/Close Out | 5.25 | 14 | 17 | Site Execution/Close Out | 0 | 1
1.9792
WorkDays (8Hrs)