## Slide 1: PIPELINES EMERGENCY REPAIR PROCESS IMPROVEMENT
LEAN DECK
Bisike-Ojiako, Chukwuma/Esangbedo, Gregory
Facilitators/CI Coaches

## Slide 2: KAIZEN EVENT ATTENDANCE
S/N | Name | Function
1 | Asen, Solomon | Security Operations
2 | Ujah, Cletus | Pipelines Operations
3 | Erewa, Johnson | Pipelines Security
4 | Soluade, Michael | Marine Logistics
5 | Eneawaji, Owo | Pipelines Operations
6 | Bisiriyu, Sunkanmi | Pipelines, Oil Spill Response
7 | Omoruyi, Iyare | Pipelines Maintenance
8 | Abani, Augustine | Pipelines HSE
9 | Jumbo, Chamberlain | Pipelines Operations
10 | Ikpe, Godwin | Pipelines Operations
11 | Aminu, Olasunmbo | Marine Logistics
12 | Ugada, Christopher | Pipelines Operations
13 | Emefiena, Ngozi | Pipelines Operations
14 | Bassey, Runyi | Pipelines HSE
15 | Bisike-Ojiako, Chucks | Continuous Improvement
16 | Esangbedo, Gregory | Continuous Improvement

## Slide 3: PIPELINE REPAIR PROCESS IMPROVEMENT – PTW/SECURITY CLEARANCE
Business Case | Scope | Critical Success Factors/Initiative Categorization
It currently takes over 6 working days to carry out the various activities involved in the Permit-to-Work and security clearance process for emergency pipeline repairs irrespective of the type of repair or location in question. This is significantly longer than the period it takes to achieve similarly important activities in the overall pipeline repair process such as containment, JIV Preparation and FTO collection. This affects the overall efficiency of the delivery of pipeline repair services with attendant cost implications to Shell’s operations arising from deferments and contravention of the Shell Corporate guidelines and the statutory requirement for containing oil spills | The review of activities involved in processing PTW/Security clearance having regard to HSE requirements | Shorter duration for achieving PTW/Security clearance flowing seamlessly into site mobilization/execution activities Alternatively simultaneous performance of some of the PTW/Security clearance activities with other activities thus eliminating current timeframe Seamless and fast delivery of the overall pipeline repair activities
Objectives | Deliverables/Timeline | Key FTE Requirement
To reduce the current time frame for performing PTW and security clearance activities by at least 80% to meet Shell’s corporate guidelines by Q1, 2015 and ensure full compliance with statutory requirements by Q4 2015 Explore the possibility of carrying out these (or some of these) activities simultaneously with other activities thereby eliminating or significantly reducing the requisite timeframe | A reviewed shortened PTW/Security Clearance Process (Q4, 2014) Earlier commencement of Site Mobilization/JIV Execution activities (Q4 2014) Standard Operating Procedure setting out the new activities/timelines for carrying out PTW/Security clearance (Q4 2015) | 1 Lean Coach: (4 months) 1 Project Manager: 4hrs/week (9 months) Other Team members: As required by the PM during the entire duration of the project
The Team | Benefits | Measures
Sponsor: Jurgen Janzen Project Manager: Asen Solomon Project Team members: Aisabokhale Tony, Erewa Johnson, Chikere Blaise, Owo Eneawaji Lean Coach: Bisike-Ojiako, Chucks | Reduction in cycle time for delivering pipeline repair activities with attendant improvement in uptake of dependant activities such as oil production activities Reduced loss of income arising from deferments attributable to defective pipelines Man hours savings from less time spent on pipeline repair activities; deployment for more value added activities | Time reduction in PTW/Security Clearance process and generally the overall pipeline repairs process as against current timeline Overall reduction in deferments attributable to delays in pipeline repair Reduced stress level on staff (assessment via questionnaires and expended man-hours) Reduced frequency of prioritization for multiple sites (support teams, GSA, Government Regulators & Contractors) Documentation approvals done within one business day (8 hours) Reduced volume of documents, approvals and document rework

## Slide 4: PIPELINE REPAIR PROCESS IMPROVEMENT - SITE MOBILIZATION/JIV EXECUTION
Business Case | Scope | Critical Success Factors/Initiative Categorization
Mobilization to site and JIV execution to perform pipeline repair activities currently takes between 17 – 23 working days depending on the type of site. This, in addition to other delays experienced in various other aspects of the repair process increases the overall duration for carrying out pipeline repairs. This affects the efficiency of the delivery of pipeline repair services with attendant loss of income to the Company arising from production deferments and contravention of the Shell Corporate guidelines and the statutory requirement for containing oil spills | The review of activities involved in site mobilization and JIV execution Activities from the PTW/Security Clearance process that constitute inputs into the mobilization/JIV execution process | Shorter duration for achieving site mobilization/JIV execution activities flowing seamlessly into Site execution/closeout activities Seamless and fast delivery of the overall pipeline repair activities
Objectives | Deliverables/Timeline | Key FTE Requirement
To reduce the current time frame for site mobilization and JIV execution by at least 80% to meet Shell’s corporate guidelines by Q1, 2015 and ensure full compliance with statutory requirements by Q4 2015 Explore the possibility of carrying out these (or some of these) activities simultaneously with other activities thereby eliminating or significantly reducing the requisite timeframe | A shortened Mobilization to site/JIV execution Process (Q4 2014) Earlier commencement of Site execution/closeout activities (Q4 2014) Standard Operating Procedure setting out the new activities/timelines for carrying out mobilization to site/JIV Execution activities (Q4 2015) | 1 Lean Coach: (4 months) 1 Project Manager: 4hrs/week (9 months) Other Team members: As required by the PM during the entire duration of the project
The Team | Benefits | Measures
Sponsor: Jurgen Janzen Project Manager: Babs Olayinka Project Team members: Anibasa Usman, Ujah Cletus, Evboifo Isaac, Soluade Michael Lean Coach: Gregory Esangbedo | Reduced cycle time for delivering pipeline repair activities with attendant improvement in uptake of dependant activities such as oil production activities Reduced loss of income arising from deferments attributable to defective pipelines Man hours savings from less time spent on pipeline repair activities; deployment of such time for more value added activities | Time reduction in site mobilization/JIV execution and generally the overall pipeline repairs process as against current timeline Overall reduction in deferments attributable to delays in pipeline repair Reduced stress level on staff (assessment via questionnaires and expended man-hours)

## Slide 5: DEFINITION OF SUCCESS
Reference Date: 31st December 2015
Definition of Success:
To achieve Joint Investigation (JIV) inspection of pipeline spillage on land and swamp within the current corporate KPI working
within normal 8 hours working period as against the 24/7 operation
Success Requirements:
Standardize all documents
F2F documentation review/approval (to include gate pass and PTW) meeting to include Warri operations
Integrate documents that lend themselves to integration
Ready availability of contractors’ resources especially for multiple site JIVs
Availability of Government Regulators for multiple site inspection
Availability of Government Security Agencies (GSAs) for multiple site inspections
Availability of Support Teams for multiple site inspections
Availability of sustained Freedom to Operate (FTO)
Prompt payment of contractors
Availability of effective field-to-field and field-to-base means of communication
Measures of Success:
JIV achieved within 3 days (Land) and 6 days (Swamp)
Documentation approvals done within one business day (8 hours)
Reduced stress level on staff (assessment via questionnaires and expended man-hours)

## Slide 6: Problem statements, solutions & ACTIONS (1/7)
S/N | Root Causes | Solutions | Actions | Action Parties | Timeframe
1 | Excessive re-work of Contractors Documents | Contractor to dedicate a document preparer/custodian | Review existing contractor documentation process and advise actions for improvement | Ujah/Aisabokhale | Q4, 2014
2 | Duplication of required documentation | Standardize required documents | Collate all required documents & review for standardization & integration | Chikere/Aisabokhale/ Ujah/Erewa/Bisiriyu/ Greg | Q4, 2014
3 | Insufficient coverage of PTW approvers at Asset Holder Level | F2F approval and delegation of authority | F2F approval and delegation of authority | Jurgen | 30/9/2014
Problem Statement 1
Poor quality contractor documentation and large volume documentation with several levels of approvals
resulting in 2-3 days delay in the process

## Slide 7: Problem statements, solutions & ACTIONS (2/7)
S/N | Root Causes | Solution | Actions | Action Party | Timeframe
1 | The ‘urgent’ requisition component of SLAs is not represented on GLMS | Logistics to engage all stakeholders for reasons of non-inclusion of GETIM component on GLMS | Engage all stakeholders for reasons of non-inclusion of GETIM option in GLMS | Mogbolu/Oludi | 30/9/2014
2 | Logistics cannot adequately support GETIM request for specific equipment | Deep Dive options to enhance contractor equipment capacity | Do trend analysis to find out how much request received for specific equipment | Mogbolu | Ditto
Problem Statement 2
Inconsistency between GLMS and agreed SLA for urgent requisition resulting in up to 1-2 days delay in
actualizing request for pipeline emergency operations

## Slide 8: Problem statements, solutions & ACTIONS (3/7)
S/N | Root Causes | Solution | Actions | Action Party | Timeframe
1 | Insufficient serviceable equipment | Conduct a deep dive on the option for procuring serviceable equipment | Conduct a deep dive on the option for procuring serviceable equipment | Agans/Jurgen | 31/12/2014
2 | GSAs not totally dedicated to SPDC operation | Secure dedicated GSA for SPDC swamp emergency operation | Secure dedicated GSA for SPDC swamp emergency operation | Jurgen/Agans | 30/09/2014
3 | Lack of prompt payment from SPDC for services rendered | Expedite cash payment for GSA services through Emergency Response Team | Expedite cash payment for GSA services through Emergency Response Team | Akinnawonu/Erewa/ Chuka Njoku/Amos Gagar | 30/09/2014
4 | Poor maintenance of equipment | Notify GSAs of poor equipment maintenance | Notify GSAs of poor equipment maintenance | Agans/Menuchim Opara | 30/09/2014
5 | Preference for cash payment for pipeline emergency activities | Expedite cash payment for GSA services through Emergency Response Team | Expedite cash payment for GSA services through Emergency Response Team | Akinnawonu/Erewa/ Chuka Njoku/Amos Gagar | 30/09/2014
Problem Statement 3
Untimely and unreliable support services from Government Security Agents (GSAs) resulting in 1-2 days downtime
(unserviceable MPV equipment, preference for cash payments)

## Slide 9: Problem statements, solutions & ACTIONS (4/7)
S/N | Root Causes | Solution | Actions | Action Party | Timeframe
1 | Limited contractor financial capacity | Effect prompt payment to contractors Equipment usage integration/optimization | Effect prompt payment to contractors Integrate/optimize company owned equipment (e.g. OSRT boats, flat bottom boats etc.) for OSRT/ Maintenance/Operations Teams | Jan Van Bunnik/Jurgen/ Greg Kuwlaski Iyare/Bisiriyu working with contractors | Continuous Continuous
2 | Contract rate not realistic with prevailing market rate for critical emergency pipeline equipment | Review contract equipment rate in line with current prevailing market rates | Review equipment rates in line with current prevailing market realities & increase number of reliable contractors when renewing the contract | Tony Aisabokhale/ Akinnawonu/Lambo/Uduak | 31/01/2015
Problem Statement 4
Lack of readily available contractor personnel & equipment for multiple site emergencies has led to 90%
prioritization of site to repair causing 3-5 days delay in repairs of subsequent sites

## Slide 10: Problem statements, solutions & ACTIONS (5/7)
S/N | Root Causes | Solution | Actions | Action Party | Timeframe
1 | Non-availability of GSM network in remote pipeline locations | Provide satellite phones | Engage IT Team to provide fit-for-purpose communication gadgets for remote locations Test reliability & effectiveness of gadgets | Aisabokhale/ Okojie Ditto | 30/09/1024 As and when available
Problem Statement 5
Non-availability of reliable field to field and field to base communication devices resulting in 6hrs – 1 day delay
in pipeline emergency operations

## Slide 11: Problem statements, solutions & ACTIONS (6/7)
S/N | Root Causes | Solution | Actions | Action Party | Timeframe
1 | Delayed evacuation of vacuum trucks & environmental barges at designated receiving facilities (terminals & flow stations) | Run an improvement project to eliminate delays in evacuation of free phase crude and vacuum trucks | Run a CI project to eliminate delays in evacuation of vacuum trucks & environmental barges | Michael Soluade/Greg/ Cletus/Anibasa | 31/12/2014
Problem Statement 6
Non-availability and inadequate numbers of logistics support equipment (environmental barges, water tankers,
fire trucks & vacuum trucks) resulting in up to 3 days delays in pipeline emergency repair activities/operations

## Slide 12: Problem statements, solutions & ACTIONS (7/7)
S/N | Root Causes | Solution | Actions | Action Party | Timeframe
1 | Uncoordinated action on JIV activity prior to take off | Improve communication of JIV timing | Review effectiveness of pre-JIV meetings | Omoruyi/Chucks | 30/09/2014
2 | No single meeting point for JIV teams | Provide a suitable waiting area for the JIV Team prior to take off Log in Registers from attendance | Provide a suitable waiting area for the JIV Team prior to take off Provide Attendance Registers for pre-JIV communications | Akinnawonu/Okojie Omoruyi | 30/12/2014 30/09/2014
Problem Statement 7
Delay in moving to JIV sites

## Slide 14: PROJECT OBJECTIVES
To collate data with which to use to understand the lead times of actual pipeline repair and lead times of the associated services supporting pipeline repair
To provide a measure of actual performance of the pipeline repair process and the dependent services associated with the process.
To drive further improvements by showing potential areas (through data analysis) in which the current process can be improved
Ongoing
Completed
Completed

## Slide 15: project schedule
We are currently here having done a Kaizen Event

## Slide 16: Project governance & APPROVALS
We have received approvals on the following:
Sign off and approval of the data analysis outcome
Approval on Project Team constitution based on Data analysis outcome
Approval to drive the 2 projects through the Lean project maturation funnel based on data analysis outcome and the schedule
  Agreed to include the Project delivery accountability in the GPAs of the persons nominated as PMs and Project Team members
Janzen, Jurgen - Pipeline Asset Manager
Aganmwonyi, Agans - GM Security
Amadi, Amadi - HSE Manager
Mogbolu, Henry - Corporate Logistics Manager
Governance
Approvals & Sign offs (already received)