## Sheet1
|  | LEAN IMPLEMENTATION TRACKING | [6 empty] | Review Date :
S/n | Recommendation | Target Schedule Reduction | Target Cost Savings | Action Party | Sponsor’s Comments/Steer & Other remarks | Pilot Project /Site | Action Person (Executor) | Target Pilot Completion | Actual Pilot Measurements |  | Remarks
[9 empty] | Schedule Reduction (days) | Cost Reduction (f$)
| PREMOB | (days) | (f$)
1 | Improve time taken to secure FTO (from 42 days to 30 days) | 12 | 0 | SD | Ok.
2 | Improve time taken to review project Security plan (from 21days to 3days ) | 18 | 0 | Security Dept | Ok. (Gabriel to draft SOP based on VSM and review with Chuks). Target:31/07/12 | Standard template for security plan in use already |  | Std template already in use |  |  | Std Security template already rolled out
3 | Improve time to review project HSE plan (29 days to 3 days) | 26 | 0 | HSE & Civil Engineering | Ok. (Gabriel to draft SOP based on VSM and review with Chuks). Target:31/07/12 | Simplified HSSE Plan produced by Contract HSE Management Team | Etsano Emmanuel | Simplified HSSE template will be deloyed before end Q4 2012 |  |  | Simplified HSSE plan will be rolled out before end 2012.
4 | Carry out equipment inspection within 3days of premob request and issue report & sticker within next 2 days. | 22 | 0 | Logistics team | Ok. (Gabriel to draft SOP based on VSM and review with Chuks). Target:31/07/12 | All pre-mobilisation inspection requests | Rohita | Outcome will be reviewed end Q1 2013 |  |  | Improvements expected after deloyment pre-mobiliastion inspection lean recommendations
5 | Improve time to secure wells for existing locations | 14 | 0 | Well Services | Depends on Production requirements. Civil Engineering to engage Well Services team. | All workover locations | Amos Trost | Outcome will be reviewed end Q1 2013 |  |  | Will be tested and reported on Agbada-57
6 | Improve time to remove flowlines in existing locations | 14 | 0 | Asset Engineering | Depends on Production requirement. Civil Eng to engage Asset Engineering team | All wokover locations | Ebere Ebeze | Outcome will be reviewed end Q1 2013 |  |  | Will be tested and reported on Agbada-57
|  | 106 | 0
HAULAGE
1 | To minimise quality & transport HSE exposures and to reduced cycle time, issue PO for location works to Contractors with asphalt within 60km of site. Deviation subject to TPE approval. | 6 | 0 | Civil Engineering | Ok . Current issue- locations already allocated to contractors at award. However, contractors will be encouraged to buy asphalt from plants near to site or establish mobile asphalt plant at site. Nearness of base to work sites shall be a condition for Tech qualification and award. | Opportunity will be explored in subsequent work assignment | Gabriel Warde | Not Applicable
2 | Relocate a set of Dura Base Materials to Gbaran field and retain a set in Kidney Island for quick intervention and reduction of logistics cost. | 5 | 60000 | Civil Eng & Prod Asset team | Ok. (10m x30m space req). The available 2 sets of durabase mats are currently in use in greater PH. A set will be relocated to Gbaran area when not in use. | To be identified based on STDWS | Gabriel Warde |  |  |  | Identified pilots are all in dry land area. Not necesary to move mats to Gbaran now
3 | Change pricing unit for haulage of Dura base mat from “per pc” to per “standard truck”. (save f$3000 per trip) | 0 | 120000 | Civil Engineering & SCM | Ok subject to opportunity in repl contract. | Not Applicable | Gabriel Warde/Francis Wilcox
4 | Use Logistics contracts for transportation of Dura base materials. | 0 | 250000 | Civil Engineering | Ok. Proper upfront planning and follow-up necessary for success. Civil contract may be deployed only at critical time frames if it is established that Logistics contract cannot meet. | Agbada-57 | Gabriel Warde
5 | Reduce long haulage distance for sand and granite | TBA | TBA | Civil Eng | Explore option for stockpiling of sand for location prep in campaign mode. Stockpiles to be established, owned and managed by contractors. |  | Gabriel Warde |  |  |  | Opportunity will be explored during the execution of the new contract
|  | 11 | 430000
CONSTRUCTION
1 | Enforce Clustering as the default option in New field development. Drill from existing slots in brown fields. Deviation shall be subject to VP-Technical’s approval. | 245 | 4000000 | Development | Ok. Lack of well as-built drawings showing trajectory of some existing wells may be an issue.
2 | Reduce the well slot spacing in high pressure wells from 6m to 5m. For a 6 slot cluster, Save 5m x 20m of piled cellar slab. | 15 | 142000 | Civil Engineering | Ok as notional. Each cluster will need specific design.
3 | Use Dura Base mat in campaign mode and when location is not planned to be revisited in the near future eg workover location. Deviation subject to TPE approval. | 34 | 342000 | Civil Engineering | Ok. Explore necessity to procure additional sets of Dura base mats. Deploy immediately at Agbda -57 | Agbada-57 | Gabriel Warde | Q1 2013 |  |  | Construction works will commence after well release in December 2012
4 | Eliminate concrete generator slab and chemical slabs and replace with asphalt surface. | 30 | 78000 | Civil Engineering | Ok. Freedom/Yinka to review Tech and HSE reqts for all concrete slabs, sub-base and pavements except cellar slab. Target:03/08/12 | Koroama SPUR-1 Epu | Gabriel Warde | Q2 2014 |  |  | Change request approved by MoC panel
5 | Eliminate waste pit. Change current waste management approach to pitless model. | 36 | 88000 | Wells | Ok subject to outcome of pilot at Koroama SPUR & EPU 1 |  | John Musa | Q2 2014 |  |  | Change request will be presented to MoC after completion of technical work by Well Engineering
6 | Reduce thickness of crushed stone base from 150mm to 100mm. | 14 | 113000 | Civil Engineering | Comments same as item 4 above. |  | Gabriel Warde | Q2 2014 |  |  | Change request approved by MoC panel
7 | Contractor to provide spare piling hammer as a standard condition for piling work. | 14 | 0 | Civil engineering | Institute periodic visual site inspection of piling equipment | All locations that require piling | Gabriel Warde |  |  |  | This recommendation is a standard practice at all piling sites
|  | 388 | 4763000
S/n | Recommendation | Schedule | Cost Savings(f$) | Action Party | Sponsor’s Comments/Steer & Other remarks
Reduction
OTHERS
1 | Release budget early for all location in the sequence to enable early commencement |  |  | Wells |  | Not Applicable | Patience Odeh
2 | Improve (standardise) Rig selection strategy . |  |  | Wells |  | Not Applicable | John Musa
3 | Stabilise drilling sequence. |  |  | Dev /Wells |  | Not Applicable
S/n | Category | No of improvement Recommedations | Potential Cycle Time Reduction | Potential Cost Savings
1 | PreMob | 6 | 106 | 0
2 | Haulage | 5 | 6 | 0
3 | Construction | 7 | 388 | 4763000
| Hard Benefits: | Soft Benefits
| Cycle Time reduction: from 8months to 5months (37.5%) | Motivated workforce & Stress reduction
| Potential cost savings of F$ 4.9mln | Improved Environmental performance; Improved Reputation
Reduced Exposure to HSE risks