## Slide 1
Pipeline Repairs Improvement Project
(Data Analysis Report out)
Chuks. Bisike-Ojiako
Greg Esangbedo
Approved By: Emeka Maduekwe

## Slide 2: Introduction & BACKGROUND
Towards the end of 2013, the PDLT initiated a CI/BI improvement on pipeline repair. The key objective of the exercise is to improve the pipeline repair process and all associated support process to the pipeline repair activity. To achieve this objective, the pipeline LT and CI decided to commence the project by gathering the necessary data - this data will help the improvement exercise focus specifically on the relevant areas that need improvement.

## Slide 3: Introduction & BACKGROUND
The Objectives of the entire project are:
To collate data with which to use to understand the lead times of actual pipeline repair and lead times of the associated services supporting pipeline repair
To provide a measure of actual performance of the pipeline repair process and the dependent services associated with the process. - !!!WE ARE HERE
To drive further improvements by showing potential areas (through data analysis) in which the current process can be improved

## Slide 4: Pipeline improvement project- draft project schedule

## Slide 5: Data collection process
Data collection started with an initial review with Pipeline Asset Manager for Steers
Draft data collection Template was produced and reviewed with all stakeholders –Pipelines Ops, Mtc, HSE, Security, etc
Feedback from the review was incorporated with a further and final review with relevant stake holders – Pipeline Mtc, Ops, HSE, Security, Logistics, etc
Data gathering commenced Wednesday 9th of April for 20 days (ended 29th April 2014)
Data was collected for each activity in the Pipeline repair process for
Land and Swamp simple operations
Swamp complex operations (cofferdam)
Normalized data was sent to all data collectors for validation on Fri 5/23/2014 11:02 validation
Results of the analysis was finalized and shared

## Slide 6: DATA ANALYSIS – KEY HIGHLIGHTS
Data was analyzed using
Simple Dot plots to ascertain independently the duration of each activity in the pipeline repair process
Pareto analysis was used to further validate the findings in the dot plot
The data analysis results indicated 2 key focus areas
  PTW/Security Clearance process Improvement
  Mobilization & JIV Execution process Improvement

## Slide 7: Data analysis outcome
Objective
Focus Area for Improvement
Focus Area for Improvement

## Slide 8: Pareto analysis
Land
Swamp
Sect Repl - Swamp

## Slide 9: Next steps
The next steps will include;
A meeting to engage Corporate HSE, Security, Logistics, Pipelines and other Stakeholders:
For a sign off and approval of the data analysis outcome
Approve the constitution of 2 CI teams (PMs, Project Teams, Sponsors) to focus on the two key areas indicated by the data analysis outcome
  Take the 2 projects through the Lean project maturation funnel based on the schedule