## Sheet1
PRE-MOBILISATION INSPECTION OF NUGI EQUIPMENT IN LATE 2010 AND 2011
S/N | DESCRIPTION OF EQUIPMENT | REG NO/ SERIAL NO | DATE PRE-MOB EXPIRED | DATE REQUEST WAS SENT | DATE OF INSPECTION | DATE INSPECTION WAS CONCLUDED | Days Request & Inspection | Days Request & Conclusion | REMARKS
A | NUGI EQUIPMENT
1 | PILING CRANE | 62180 | 2010-08-14 | 2010-11-01 | 2010-11-26 | 2010-11-26 | 25 | -24 | Premob inspection initially stopped by Project Engineer due to poor condition of crane on 03/11/2011. Contractor carried out refurbishment works on crane and later presented for inspection later
2 | FORD MEDEVAC VEHICLE | EG 956 PHC | 2010-12-07 | 2010-12-17 | 2011-01-11 | 2011-01-11 | 24 | -24 | Inspection delayed by Xmas/New year holidays
3 | FORD MOBILE CONCRETE MIXER | XV 559 PHC | NEW REQUEST | 2011-01-11 | 01/02/2011; 10/02/2011 | 2011-02-23 | #VALUE! | -41 | Equipment failed inspections on 2 occasions and passed at the 3rd inspection
4 | FORD MOBILE CONCRETE MIXER | XV 560 PHC | NEW REQUEST | 2011-01-11 | 01/02/2011; 10/02/2011 |  | #VALUE! |  | Inspection not concluded as equipment failed on both occasions
5 | SILAN CONCRETE MIXER | CM-001/1254 | NEW REQUEST | 2011-01-11 | 01/02/2011; 10/02/2011 | 2011-02-23 | #VALUE! | -41 | Equipment failed inspections on 2 occasions and passed at the 3rd inspection
6 | CAT 980 WHEEL LOADER | GT-WL008 | NEW REQUEST | 2011-01-29 | 2011-02-10 | 2011-03-28 | 11 | -56 | Did not passed inspection on 10/02/2011 but passed on re-scheduled inspection on 28/03/2011
7 | ATLASCO GENERATOR |  | NEW REQUEST | 2011-01-29 | 2011-03-17 | 2011-03-17 | 48 | -45 | Premob inspection delayed by inability of Contractor to earth the Generator on time.
8 | GROVE CRANE | CR-003 -70 | NEW REQUEST | 2011-02-02 | 2011-02-10 | 2011-03-21 | 8 | -45 | Did not passed inspection on 10/02/2011 but passed on re-scheduled inspection at site on 21/03/2011
9 | GROVE CRANE | CR-005 -65 | NEW REQUEST | 2011-02-02 | 2011-02-10 |  | 8 |  | Failed premob inspection and has not been re-presented for inspection
10 | TOYOTA HIACE BUS | AM 195 DBU | NEW REQUEST | 2011-02-07 | 2011-02-08 | 2011-02-08 | 1 | 0 | Inspection carried out in IA and concluded same day
11 | TOYOTA HIACE BUS | AM 194 DBU | NEW REQUEST | 2011-02-09 | 2011-02-09 | 2011-02-09 | 0 | 1 | Inspection carried out in IA and concluded same day
12 | FORD WATER TANKER | XA 772 NDU | NEW REQUEST | 2011-02-17 | 2011-03-07 |  | 20 |  | Failed premob due to cracked windscreen
13 | FORD MOBILE CONCRETE MIXER | XV 561 PHC | NEW REQUEST | 2011-02-19 | 2011-03-07 | 2011-03-07 | 18 | -15 | Premob inspection completed on date of inspection
14 | FORD MOBILE CONCRETE MIXER | XV 560 PHC | NEW REQUEST | 2011-02-19 | 2011-03-07 | 2011-03-07 | 18 | -15 | Re-scheduled inspection after the equipment failed initial premob
15 | LINCOLN ELECTRIC WELDING MACHINE | S-53878 | NEW REQUEST | 2011-03-04 | 2011-03-17 | 2011-03-17 | 13 | -12 | Passed inspection at first instance
16 | CAT 312L EXCAVATOR |  | NEW REQUEST | 2011-03-14 | 2011-03-14 |  | 0 |  | Failed premob due to cracked windscreen. Inspection team was already in Gbaran and carried out inspection sameday request was made
17 | CAT WATER TANKER | 88W6558 | NEW REQUEST | 2011-03-14 | 2011-03-17 | 2011-03-17 | 3 | -2 | Inspection successfully done
18 | CAT D5H DOZER | DZ-004 | 2011-01-11 | 2011-03-28 |  |  | -40048 |  | Premob inspection planned for 05/04/2011 but re-scheduled for 13/04/2011 due to logistic problems encountered by premob inspection team.
19 | BOMAG VIBRO ROLLER | VR-003 | 2011-01-11 | 2011-03-29 |  |  | -40049
20 | CAT 140G GRADER | MG-002 | 2011-01-11 | 2011-03-29 |  |  | -40049
21 | CAT VIBRO COMPACTOR | VC-001 | 2011-01-11 | 2011-03-29 |  |  | -40049
B | SUB-CONTRACTOR (TREVI) EQUIPMENT | [5 empty] | 0
1 | PILING CRANE | TF-2032 |  | 2011-02-25 | 2011-03-22 | 2011-03-22 | 27 | -24 | Premob team required the piling crane + hammer to be set up at site before inspection
2 | PILING HAMMER | TF-2614 |  | 2011-02-25 | 2011-03-22 | 2011-03-22 | 27 | -24
3 | LOCATELI CRANE | TF-1987 |  | 2011-02-25 | 2011-03-03 | 2011-03-03 | 8 | -5 | Passed inspection at first instance
4 | PAYLOADER | TF-2351 |  | 2011-02-25 | 2011-03-17 | 2011-03-17 | 22 | -19 | Equipment availability delayed by Contractor
5 | WELDING MACHINE | TF-4659 |  | 2011-02-25 | 2011-03-17 | 2011-03-17 | 22 | -19
#NAME?

## Sheet2
PRE-MOBILISATION INSPECTION OF NUGI EQUIPMENT IN LATE 2010 AND 2011
S/N | DESCRIPTION OF EQUIPMENT | REG NO/ SERIAL NO | DATE PRE-MOB EXPIRED | DATE REQUEST WAS SENT | DATE OF INSPECTION | DATE INSPECTION WAS CONCLUDED | Days Difference | LOGISTICS SLA | Average | REMARKS
1 | PILING CRANE | 62180 | 2010-08-14 | 2010-11-01 | 2010-11-26 | 2010-11-26 | 25 | 3 | 25 | Premob inspection initially stopped by Project Engineer due to poor condition of crane on 03/11/2011. Contractor carried out refurbishment works on crane and later presented for inspection later
2 | FORD MEDEVAC VEHICLE | EG 956 PHC | 2010-12-07 | 2010-12-17 | 2011-01-11 | 2011-01-11 | 24 | 3 | 25 | Inspection delayed by Xmas/New year holidays
3 | FORD MOBILE CONCRETE MIXER | XV 559 PHC | NEW REQUEST | 2011-01-11 | 01/02/2011; 10/02/2011 | 2011-02-23 | 42 | 3 | 25 | Equipment failed inspections on 2 occasions and passed at the 3rd inspection
5 | SILAN CONCRETE MIXER | CM-001/1254 | NEW REQUEST | 2011-01-11 | 01/02/2011; 10/02/2011 | 2011-02-23 | 42 | 3 | 25 | Equipment failed inspections on 2 occasions and passed at the 3rd inspection
6 | CAT 980 WHEEL LOADER | GT-WL008 | NEW REQUEST | 2011-01-29 | 2011-02-10 | 2011-03-28 | 59 | 3 | 25 | Did not passed inspection on 10/02/2011 but passed on re-scheduled inspection on 28/03/2011
7 | ATLASCO GENERATOR |  | NEW REQUEST | 2011-01-29 | 2011-03-17 | 2011-03-17 | 48 | 3 | 25 | Premob inspection delayed by inability of Contractor to earth the Generator on time.
8 | GROVE CRANE | CR-003 -70 | NEW REQUEST | 2011-02-02 | 2011-02-10 | 2011-03-21 | 49 | 3 | 25 | Did not passed inspection on 10/02/2011 but passed on re-scheduled inspection at site on 21/03/2011
10 | TOYOTA HIACE BUS | AM 195 DBU | NEW REQUEST | 2011-02-07 | 2011-02-08 | 2011-02-08 | 1 | 3 | 25 | Inspection carried out in IA and concluded same day
11 | TOYOTA HIACE BUS | AM 194 DBU | NEW REQUEST | 2011-02-09 | 2011-02-09 | 2011-02-09 | 0 | 3 | 25 | Inspection carried out in IA and concluded same day
13 | FORD MOBILE CONCRETE MIXER | XV 561 PHC | NEW REQUEST | 2011-02-19 | 2011-03-07 | 2011-03-07 | 18 | 3 | 25 | Premob inspection completed on date of inspection
14 | FORD MOBILE CONCRETE MIXER | XV 560 PHC | NEW REQUEST | 2011-02-19 | 2011-03-07 | 2011-03-07 | 18 | 3 | 25 | Re-scheduled inspection after the equipment failed initial premob
15 | LINCOLN ELECTRIC WELDING MACHINE | S-53878 | NEW REQUEST | 2011-03-04 | 2011-03-17 | 2011-03-17 | 13 | 3 | 25 | Passed inspection at first instance
16 | CAT WATER TANKER | 88W6558 | NEW REQUEST | 2011-03-14 | 2011-03-17 | 2011-03-17 | 3 | 3 | 25 | Inspection successfully done
17 | PILING CRANE | TF-2032 |  | 2011-02-25 | 2011-03-22 | 2011-03-22 | 27 | 3 | 25 | Premob team required the piling crane + hammer to be set up at site before inspection
18 | PILING HAMMER | TF-2614 |  | 2011-02-25 | 2011-03-22 | 2011-03-22 | 27 | 3 | 25
19 | LOCATELI CRANE | TF-1987 |  | 2011-02-25 | 2011-03-03 | 2011-03-03 | 8 | 3 | 25 | Passed inspection at first instance
20 | PAYLOADER | TF-2351 |  | 2011-02-25 | 2011-03-17 | 2011-03-17 | 22 | 3 | 25 | Equipment availability delayed by Contractor
21 | WELDING MACHINE | TF-4659 |  | 2011-02-25 | 2011-03-17 | 2011-03-17 | 22 | 3 | 25
24.8889

## Sheet3
S/N | EQUIPMENT | REG NO/ SERIAL NO | DATE PRE-MOB EXPIRED | DATE REQUEST WAS SENT | DATE OF INSPECTION | DATE INSPECTION WAS CONCLUDED | Days Request & Inspection | Days Request & Conclusion | Premob SLA | REMARKS
1 | PILING CRANE | 62180 | 2010-08-14 | 2010-11-01 | 2010-11-26 | 2010-11-26 | 25 | 25 | 3 | Premob inspection initially stopped by Project Engineer due to poor condition of crane on 03/11/2011. Contractor carried out refurbishment works on crane and later presented for inspection later
2 | FORD MEDEVAC VEHICLE | EG 956 PHC | 2010-12-07 | 2010-12-17 | 2011-01-11 | 2011-01-11 | 24 | 24 | 3 | Inspection delayed by Xmas/New year holidays
3 | FORD MOBILE CONCRETE MIXER | XV 559 PHC | NEW REQUEST | 2011-01-11 | 2011-02-10 | 2011-02-23 | 29 | 42 | 3 | Equipment failed inspections on 2 occasions and passed at the 3rd inspection
#REF! | SILAN CONCRETE MIXER | CM-001/1254 | NEW REQUEST | 2011-01-11 | 2011-02-10 | 2011-02-23 | 29 | 42 | 3 | Equipment failed inspections on 2 occasions and passed at the 3rd inspection
#REF! | CAT 980 WHEEL LOADER | GT-WL008 | NEW REQUEST | 2011-01-29 | 2011-02-10 | 2011-03-28 | 11 | 59 | 3 | Did not passed inspection on 10/02/2011 but passed on re-scheduled inspection on 28/03/2011
#REF! | ATLASCO GENERATOR |  | NEW REQUEST | 2011-01-29 | 2011-03-17 | 2011-03-17 | 48 | 48 | 3 | Premob inspection delayed by inability of Contractor to earth the Generator on time.
#REF! | GROVE CRANE | CR-003 -70 | NEW REQUEST | 2011-02-02 | 2011-02-10 | 2011-03-21 | 8 | 49 | 3 | Did not passed inspection on 10/02/2011 but passed on re-scheduled inspection at site on 21/03/2011
#REF! | TOYOTA HIACE BUS | AM 195 DBU | NEW REQUEST | 2011-02-07 | 2011-02-08 | 2011-02-08 | 1 | 1 | 3 | Inspection carried out in IA and concluded same day
#REF! | TOYOTA HIACE BUS | AM 194 DBU | NEW REQUEST | 2011-02-09 | 2011-02-09 | 2011-02-09 | 0 | 0 | 3 | Inspection carried out in IA and concluded same day
#REF! | FORD MOBILE CONCRETE MIXER | XV 561 PHC | NEW REQUEST | 2011-02-19 | 2011-03-07 | 2011-03-07 | 18 | 18 | 3 | Premob inspection completed on date of inspection
#REF! | FORD MOBILE CONCRETE MIXER | XV 560 PHC | NEW REQUEST | 2011-02-19 | 2011-03-07 | 2011-03-07 | 18 | 18 | 3 | Re-scheduled inspection after the equipment failed initial premob
#REF! | LINCOLN ELECTRIC WELDING MACHINE | S-53878 | NEW REQUEST | 2011-03-04 | 2011-03-17 | 2011-03-17 | 13 | 13 | 3 | Passed inspection at first instance
#REF! | CAT WATER TANKER | 88W6558 | NEW REQUEST | 2011-03-14 | 2011-03-17 | 2011-03-17 | 3 | 3 | 3 | Inspection successfully done
1 | PILING CRANE | TF-2032 |  | 2011-02-25 | 2011-03-22 | 2011-03-22 | 27 | 27 | 3 | Premob team required the piling crane + hammer to be set up at site before inspection
2 | PILING HAMMER | TF-2614 |  | 2011-02-25 | 2011-03-22 | 2011-03-22 | 27 | 27 | 3
3 | LOCATELI CRANE | TF-1987 |  | 2011-02-25 | 2011-03-03 | 2011-03-03 | 8 | 8 | 3 | Passed inspection at first instance
4 | PAYLOADER | TF-2351 |  | 2011-02-25 | 2011-03-17 | 2011-03-17 | 22 | 22 | 3 | Equipment availability delayed by Contractor
5 | WELDING MACHINE | TF-4659 |  | 2011-02-25 | 2011-03-17 | 2011-03-17 | 22 | 22 | 3