## Slide 1: PIPELINE REPAIR PROCESS IMPROVEMENT – SITE MOBILIZATION/JIV EXECUTION
Business Case | Scope | Critical Success Factors/Initiative Categorization
Mobilization to site to perform pipeline repair activities currently takes between 30 -35 working days depending on the type of site. This excludes an additional 20 days or so spent on JIV execution. This, in addition to other delays experienced in various other aspects of the repair process increases the overall duration for carrying out pipeline repairs. This affects the efficiency of the delivery of pipeline repair services with attendant loss of income to the Company arising from production deferments | The review of activities involved in site mobilization and JIV execution Activities from the PTW/Security Clearance process that constitute inputs into the mobilization/JIV execution process | Shorter duration for achieving site mobilization/JIV execution activities flowing seamlessly into Site execution/closeout activities Seamless and fast delivery of the overall pipeline repair activities
Objectives | Deliverables/Timeline | Key FTE Requirement
To reduce the current time frame for mobilizing to site and JIV execution by at least ...% without compromising HSE requirements | A shortened Mobilization to site/JIV execution Process (31st July 2014) Earlier commencement of Site execution/closeout activities (31st July 2014) Standard Operating Procedure setting out the new activities/timelines for carrying out mobilization to site/JIV Execution activities (31st October 2014) | 1 Lean Coach: (4 months) 1 Project Manager: 4hrs/week (9 months) Other Team members: As required by the PM during the entire duration of the project
The Team | Benefits | Measures
Sponsors: Jurgen Janzen, Amadi Amadi Project Manager: Babs Olayinka Project Team members: Anibasa Usman, Ujah Cletus, Evboifo Isaac, Soluade Michael Lean Coach: Gregory Esangbedo | Reduced cycle time for delivering pipeline repair activities with attendant improvement in uptake of dependant activities such as oil production activities Reduced loss of income arising from deferments attributable to defective pipelines Man hours savings from less time spent on pipeline repair activities; deployment of such time for more value added activities | Time reduction in site mobilization/JIV excution as against current timeline Time reduction in completing the overall pipeline repairs process as against current timeline Overall % reduction in deferments attributable to delays in pipeline repair