## Marginal Swamp Location
Practitioner Name | C.C Bisike-Ojiako
Process | Location Preperation
Process Step No
Step # | 1 | 2 | 3 | 4 | 5
Lead Time | 2wks | 2wks | 3wks | 2wks | 1wk
Value Added Time | 1day | 2days | 1day | 1day | 1day
Quality or RFT%
Cost ($)
Step # | 1 | 2 | 3 | 4 | 5
Lead Time | 2wks | 1wk | 1day | 2wks | 2wks
Value Added Time | 3days | 1day | 1day | 3days | 2days
Quality or RFT%
Cost ($)
| 146508.252 | 73254.126 |  | 12209.021 | 12209.021
244180.42
Step # | 1 | 2 | 3 | 4 | 5 | 6 | 7
Lead Time | 2wks | 2wks | 1wk | 16-48wks | 1wk | 2wks | 3wks
Value Added Time | 1wk | 1wk | 1wk | 12-40wks | 3days | 7days | 4days
Quality or RFT%
Cost ($) | 19796.9808 | 162587.0267 | 3762.5 | 1200196.4748 | 139444.6667 |  | 306554.1093
Step # | 1 | 2 | 3 | 4
Lead Time | 8wks | 4wks | 1wk | 12wks
Value Added Time | 6wks | 2wks | 1day | 8wks
Quality or RFT%
Cost ($) | 271626 | 54325.2 |  | 217300.8
543252
Step # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 8
Lead Time | 5wks | 3wks | 2wks | 6wks | 4wks | 2wks | 4wks | 8wks | 8wks
Value Added Time | 3wks | 1wk | 1wk | 4wks | 3wks | 1wk | 3wks | 6wks | 6wks
Quality or RFT%
Cost ($) | 98308.3267 | 47102.2067 | 456714.5717 | 130497.6867 | 466798.6291 | 16218.45 | 26443.9533 | 81509.62 | 193727.8333
Step # | 1 | 2 | 3
Lead Time | 2wks | 2wks | 1wk
Value Added Time | 4days | 4days | 4days
Quality or RFT%
Cost ($) | 132265 | 44088.3333 | 44088.3333
220441.6667
Step # | 1 | 2 | 3 | 4
Lead Time | 2wks | 1wk | 1day | 1wk
Value Added Time | 3days | 2days | 1day | 1day
Quality or RFT%
Cost ($) | 24176.778 | 145060.668 | 72530.334
241767.78
Equipment Inspection
Security Plan
JHA
HSE Manual
Medical Certificate
Start
Method Statement/Procedure
Quality Plan
Premobilisation
Premobilisation
Premobilisation
Premobilisation
Premobilisation
Equiment move to site
HSE workshop
Induction of workers
Set up site offices
Personnel move to site
Start
Set up store/ Toilet
Mobilisation
Mobilisation
Mobilisation
Mobilisation
Mobilisation
Fabricate piles
Set up piling rig
Install piles
Transport piles to location
Starts
Piling
Piling
Piling
Piling
Generator slab
Cellar slab/Pit
Waste Pit
Chemical Slab
Mud Tank
Concrete Works
Bush clearing
Construction of Bundwall
Sandfilling
Stripping
Start
Stabilisation
Earthworks
Earthworks
Earthworks
Earthworks
Earthworks
Earthworks
Earthworks
Compaction/Curing
Crushed stone
Earthworks
Concrete Works
Concrete Works
Concrete Works
Concrete Works
Cement Slab
Evacuation Pits
Concrete Works
Concrete Works
Perimeter Drain
Concrete Works
Haul Asphalt to site
Roll Asphalt
Pave
Start
Asphalting
Mobilisation
Asphalting
Asphalting
Remove Excess Materials from site.
Demob Personnel from site
Handover Location
Demob equiment from site
Start
Demobilisation
Demobilisation
Mobilisation
Demobilisation
Demobilisation
Fencing
Concrete Works

## Land Location
Practitioner Name | C.C Bisike-Ojiako
Process | Location Preperation
Process Step No
Step # | 1 | 2 | 3 | 4 | 5
Lead Time | 2wks | 2wks | 3wks | 2wks | 1wk
Value Added Time | 1day | 2days | 1day | 1day | 1day
Quality or RFT%
Cost ($)
Step # | 1 | 2 | 3 | 4 | 5
Lead Time | 2wks | 1wk | 1day | 2wks | 2wks
Value Added Time | 3days | 1day | 1day | 3days | 2days
Quality or RFT%
Cost ($)
| 131129.16 | 65564.58 |  | 10927.43 | 10927.43
218548.6
Step # | 1 | 2 |  | 4 | 5 |  | 7
Lead Time | 2wks | 2wks |  | 8wks | 1wk |  | 3wks
Value Added Time | 1wk | 1wk |  | 6wks | 3days |  | 4days
Quality or RFT%
Cost ($) | 10720.9 | 62342 |  | 169496.25 | 129896.6667 |  | 199689.91
Step # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 8
Lead Time | 5wks | 3wks | 2wks | 6wks | 4wks | 2wks | 4wks | 8wks | 8wks
Value Added Time | 3wks | 1wk | 1wk | 4wks | 3wks | 1wk | 3wks | 6wks | 6wks
Quality or RFT%
Cost ($) | 98308.3267 | 47102.2067 | 456714.5717 | 130497.6867 | 466798.6291 | 16218.45 | 26443.9533 | 81509.62 | 193727.8333
Step # | 1 | 2 | 3
Lead Time | 2wks | 2wks | 1wk
Value Added Time | 4days | 4days | 4days
Quality or RFT%
Cost ($) | 132265 | 44088.3333 | 44088.3333
220441.6667
Step # | 1 | 2 | 3 | 4
Lead Time | 2wks | 1wk | 1day | 1wk
Value Added Time | 3days | 2days | 1day | 1day
Quality or RFT%
Cost ($) | 24176.778 | 145060.668 | 72530.334
241767.78
Equipment Inspection
Security Plan
JHA
HSE Manual
Medical Certificate
Start
Method Statement/Procedure
Quality Plan
Premobilisation
Premobilisation
Premobilisation
Premobilisation
Premobilisation
Equiment move to site
HSE workshop
Induction of workers
Set up site offices
Personnel move to site
Start
Set up store/ Toilet
Mobilisation
Mobilisation
Mobilisation
Mobilisation
Mobilisation
Generator slab
Cellar slab/Pit
Waste Pit
Chemical Slab
Mud Tank
Concrete Works
Bush clearing
Sandfilling
Stripping
Start
Stabilisation
Earthworks
Earthworks
Earthworks
Earthworks
Earthworks
Earthworks
Earthworks
Compaction/Curing
Crushed stone
Earthworks
Concrete Works
Concrete Works
Concrete Works
Concrete Works
Cement Slab
Evacuation Pits
Concrete Works
Concrete Works
Perimeter Drain
Concrete Works
Haul Asphalt to site
Roll Asphalt
Pave
Start
Asphalting
Mobilisation
Asphalting
Asphalting
Remove Excess Materials from site.
Demob Personnel from site
Handover Location
Demob equiment from site
Start
Demobilisation
Demobilisation
Mobilisation
Demobilisation
Demobilisation
Fencing
Concrete Works