## MainData
NO | ACTIVITY | DESCRIPTION | VATmins | PLTmins | VATdays | PLTdays | Month | Costs
1 | PreMob-PO | ISSUE PO | 5 | 6720 | 0.010417 | 14 | 0.63636
2 | PreMob-HSE1 | Contractor submit HSE, JHA plan | 5 | 10080 | 0.010417 | 21 | 0.95455
3 | PreMob-HSE2 | Proj Eng review HSE plan | 480 | 1440 | 1 | 3 | 0.13636
4 | PreMob-HSE3 | HSE Adv review HSE plan | 480 | 1440 | 1 | 3 | 0.13636
5 | PreMob-HSE4 | Contract Holder review plan | 480 | 1920 | 1 | 4 | 0.18182
6 | PreMob-HSE5 | Contract Owner review plan | 480 | 3360 | 1 | 7 | 0.31818
7 | PreMob-HSE6 | Hold Challenge session | 480 | 3360 | 1 | 7 | 0.31818
8 | PreMob-EQ1 | Contractor Submit Equipment list | 5 | 6720 | 0.010417 | 14 | 0.63636
9 | PreMob-EQ2 | Send Equip list to Logistics | 5 | 158.4 | 0.010417 | 0.33 | 0.015
10 | PreMob-EQ3 | Inspect Equipment (Premob) | 960 | 13440 | 2 | 28 | 1.2727
11 | PreMob-SEC1 | Contractor submit Security plan | 5 | 3360 | 0.010417 | 7 | 0.31818
12 | PreMob-SEC2 | Send Security plan to ASA | 5 | 0 | 0.010417 |  | 0
13 | PreMob-SEC3 | Approve Security plan | 2 | 10080 | 0.0041667 | 21 | 0.95455
14 | PreMob-FTO | Obtain FTO | 480 | 20160 | 1 | 42 | 1.9091
15 | PreMob-HSE7 | Issue Premob Cert | 5 | 16800 | 0.010417 | 35 | 1.5909
16 | PreMob-TRN1 | Contractor move EQP/PERS to site | 1440 | 6720 | 3 | 14 | 0.63636 | 300000
17 | PreMob-HSE8 | Conduct HSE Induction | 480 | 3360 | 1 | 7 | 0.31818
18 | PreMob-OFF | Set up Site office | 480 | 3360 | 1 | 7 | 0.31818
19 | PreMob-MED | Medical Certification | 480 | 4800 | 1 | 10 | 0.45455
20 | Bush Clearing | Bush Clearing | 3360 | 4800 | 7 | 10 | 0.45455 | 20000
21 | Stripping | Stripping | 2400 | 3360 | 5 | 7 | 0.31818 | 95000
22 | SandFilling | SandFilling | 13440 | 26880 | 28 | 56 | 2.5455 | 700000
23 | ConcreteWorks1 | Hardcore | 9120 | 29760 | 19 | 62 | 2.8182
24 | ConcreteWorks2 | Excavation | 39840 | 62880 | 83 | 131 | 5.9545
25 | ConcreteWorks3 | Blinding | 22080 | 47520 | 46 | 99 | 4.5
26 | ConcreteWorks4 | Reinforcement Fixing | 43200 | 72000 | 90 | 150 | 6.8182
27 | ConcreteWorks5 | Formwok | 43680 | 70080 | 91 | 146 | 6.6364
28 | ConcreteWorks6 | Concrete Casting | 55680 | 111360 | 116 | 232 | 10.5455
29 | ConcreteWorks7 | Curing | 127680 | 127680 | 266 | 266 | 12.0909
30 | ConcreteSlabs1 | Waste Pit | 35520 | 71520 | 74 | 149 | 6.7727 | 130000
31 | ConcreteSlabs2 | Gen Slab | 26400 | 39840 | 55 | 83 | 3.7727 | 100000
32 | ConcreteSlabs3 | Mud Tank | 39360 | 39360 | 82 | 82 | 3.7273 | 230000
33 | ConcreteSlabs4 | Cement Slab | 16800 | 20160 | 35 | 42 | 1.9091 | 20000
34 | ConcreteSlabs5 | Evacuation Pit | 20160 | 24000 | 42 | 50 | 2.2727 | 30000
35 | ConcreteSlabs6 | Cellat Pit/Slab/Flowline trench | 111360 | 162720 | 232 | 339 | 15.4091 | 240000
36 | ConcreteSlabs7 | Perimeter Drains | 44640 | 44640 | 93 | 93 | 4.2273 | 80000
37 | ConcreteSlabs8 | Fencing | 38880 | 59040 | 81 | 123 | 5.5909 | 183000
38 | ConcreteSlabs9 | Septic Tank/Soakaway | 8160 | 14400 | 17 | 30 | 1.3636 | 24000
39 | CementStab | Cement Slab | 3360 | 6720 | 7 | 14 | 0.63636 | 138000
40 | BaseCourse | Base Course | 2400 | 13440 | 5 | 28 | 1.2727 | 300000
41 | AshpaltSurf1 | MC1 | 960 | 4800 | 2 | 10 | 0.45455 | 20000
42 | AshpaltSurf2 | Colas | 3360 | 1612800 | 7 | 3360 | 152.7273 | 17000
43 | AshpaltSurf3 | Apply Ashpalt wearing course | 3360 | 13440 | 7 | 28 | 1.2727 | 197000
44 | DEMOB1 | Clean Site | 3360 | 6720 | 7 | 14 | 0.63636
45 | DEMOB2 | Remove EQP/PERS from site | 3360 | 6720 | 7 | 14 | 0.63636 | 293000
46 | PreparedLoc | Prepared Location | 0 | 0 | 0 | 0 | 0 | 0
Mins |  |  | 728677 | 2813918.4 | 1518.0771 | 5862.33 |  | 3117000
Hours |  |  | 12144.6167 | 46898.64
Days |  |  | 1518.0771 | 5862.33
Months |  |  | 69.0035 | 266.4695 |  |  | 266.4695

## workday
Work Day
Day | Hrs | Mins | Sec
1 | 8 | 480 | 28800

## Sheet2
NO | ACTIVITY | DESCRIPTION | VATmins | PLTmins | VATdays | PLTdays | Costs
1 | PreMob-PO | ISSUE PO | 5 | 6720 | 0.010417 | 14
2 | PreMob-HSE1 | Contractor submit HSE, JHA plan | 5 | 10080 | 0.010417 | 21
3 | PreMob-HSE2 | Proj Eng review HSE plan | 480 | 1440 | 1 | 3
4 | PreMob-HSE3 | HSE Adv review HSE plan | 480 | 1440 | 1 | 3
5 | PreMob-HSE4 | Contract Holder review plan | 480 | 1920 | 1 | 4
6 | PreMob-HSE5 | Contract Owner review plan | 480 | 3360 | 1 | 7
7 | PreMob-HSE6 | Hold Challenge session | 480 | 3360 | 1 | 7
8 | PreMob-EQ1 | Contractor Submit Equipment list | 5 | 6720 | 0.010417 | 14
9 | PreMob-EQ2 | Send Equip list to Logistics | 5 | 158.4 | 0.010417 | 0.33
10 | PreMob-EQ3 | Inspect Equipment (Premob) | 960 | 13440 | 2 | 28
11 | PreMob-SEC1 | Contractor submit Security plan | 5 | 3360 | 0.010417 | 7
12 | PreMob-SEC2 | Send Security plan to ASA | 5 | 0 | 0.010417
13 | PreMob-SEC3 | Approve Security plan | 2 | 10080 | 0.0041667 | 21
14 | PreMob-FTO | Obtain FTO | 480 | 20160 | 1 | 42
15 | PreMob-HSE7 | Issue Premob Cert | 5 | 16800 | 0.010417 | 35
16 | PreMob-TRN1 | Contractor move EQP/PERS to site | 1440 | 6720 | 3 | 14 | 300000
17 | PreMob-HSE8 | Conduct HSE Induction | 480 | 3360 | 1 | 7
18 | PreMob-OFF | Set up Site office | 480 | 3360 | 1 | 7
19 | PreMob-MED | Medical Certification | 480 | 4800 | 1 | 10
20 | Bush Clearing | Bush Clearing | 3360 | 4800 | 7 | 10 | 20000
21 | Stripping | Stripping | 2400 | 3360 | 5 | 7 | 95000
22 | SandFilling | SandFilling | 13440 | 26880 | 28 | 56 | 700000
23 | ConcreteWorks1 | Hardcore | 9120 | 29760 | 19 | 62
24 | ConcreteWorks2 | Excavation | 39840 | 62880 | 83 | 131
25 | ConcreteWorks3 | Blinding | 22080 | 47520 | 46 | 99
26 | ConcreteWorks4 | Reinforcement Fixing | 43200 | 72000 | 90 | 150
27 | ConcreteWorks5 | Formwok | 43680 | 70080 | 91 | 146
28 | ConcreteWorks6 | Concrete Casting | 55680 | 111360 | 116 | 232
29 | ConcreteWorks7 | Curing | 127680 | 127680 | 266 | 266
30 | ConcreteSlabs1 | Waste Pit | 35520 | 71520 | 74 | 149 | 130000
31 | ConcreteSlabs2 | Gen Slab | 26400 | 39840 | 55 | 83 | 100000
32 | ConcreteSlabs3 | Mud Tank | 39360 | 39360 | 82 | 82 | 230000
33 | ConcreteSlabs4 | Cement Slab | 16800 | 20160 | 35 | 42 | 20000
34 | ConcreteSlabs5 | Evacuation Pit | 20160 | 24000 | 42 | 50 | 30000
35 | ConcreteSlabs6 | Cellat Pit/Slab/Flowline trench | 111360 | 162720 | 232 | 339 | 240000
36 | ConcreteSlabs7 | Perimeter Drains | 44640 | 44640 | 93 | 93 | 80000
37 | ConcreteSlabs8 | Fencing | 38880 | 59040 | 81 | 123 | 183000
38 | ConcreteSlabs9 | Septic Tank/Soakaway | 8160 | 14400 | 17 | 30 | 24000
39 | CementStab | Cement Slab | 3360 | 6720 | 7 | 14 | 138000
40 | BaseCourse | Base Course | 2400 | 13440 | 5 | 28 | 300000
41 | AshpaltSurf1 | MC1 | 960 | 4800 | 2 | 10 | 20000
42 | AshpaltSurf2 | Colas | 3360 | 1612800 | 7 | 3360 | 17000
43 | AshpaltSurf3 | Apply Ashpalt wearing course | 3360 | 13440 | 7 | 28 | 197000
44 | DEMOB1 | Clean Site | 3360 | 6720 | 7 | 14
45 | DEMOB2 | Remove EQP/PERS from site | 3360 | 6720 | 7 | 14 | 293000
46 | PreparedLoc | Prepared Location | 0 | 0 | 0 | 0 | 0

## ConcreteWorks
|  | Waste Pit |  | Gen Slab |  | Mud Tank Slab |  | Cement Slab |  | Evacuation Pit |  | Cellar Pit |  | Cella Slab |  | Flowline Trench |  | Perimeter Drains |  | Fencing |  | Septic Tank/Soakaway
|  | VA | LT | VA | LT | VA | LT | VA | LT | VA | LT | VA | LT | VA | LT | VA | LT | VA | LT | VA | LT | VA | LT
1 | Hardcore | 0 | 0 | 3 | 14 | 7 | 28 | 1 | 3 | 0 | 0 | 1 | 3 | 7 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Excavation | 7 | 21 | 3 | 1 | 7 | 12 | 1 | 2 | 3 | 5 | 5 | 8 | 3 | 5 | 10 | 14 | 21 | 28 | 21 | 28 | 2 | 7
3 | Blinding | 4 | 9 | 3 | 6 | 7 | 18 | 1 | 2 | 1 | 2 | 1 | 3 | 5 | 10 | 7 | 12 | 8 | 18 | 8 | 18 | 1 | 1
4 | Reinforcement Fixing | 7 | 28 | 7 | 12 | 12 | 14 | 1 | 2 | 3 | 5 | 5 | 7 | 15 | 21 | 18 | 28 | 10 | 14 | 10 | 14 | 2 | 5
5 | Formwork | 21 | 35 | 5 | 10 | 7 | 12 | 1 | 1 | 2 | 3 | 4 | 7 | 5 | 8 | 18 | 25 | 12 | 21 | 14 | 21 | 2 | 3
6 | Concrete Casting | 7 | 28 | 6 | 12 | 14 | 21 | 2 | 4 | 5 | 7 | 2 | 7 | 21 | 48 | 21 | 35 | 14 | 28 | 21 | 35 | 3 | 7
7 | Curing | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 7 | 7 | 7 | 7
| Cost | 130k |  | 100k |  | 230k |  | 20k |  | 30k |  | 240k | [5 empty] | 80k |  | 183k |  | 24k
|  | VATmins | PLTmins | VATdays | PLTdays | Cost
| Hardcore |  |  | 19 | 62
| Excavation |  |  | 83 | 131
| Blinding |  |  | 46 | 99
| Reinforcement Fixing |  |  | 90 | 150
| Formwork |  |  | 91 | 146
| Concrete Casting |  |  | 116 | 232
| Curing |  |  | 266 | 266
Cost
| Waste Pit |  |  | 74 | 149 | 130000
| Gen Slab |  |  | 55 | 83 | 100000
| Mud Tank |  |  | 82 | 82 | 230000
| Cement Slab |  |  | 35 | 42 | 20000
| Evacuation Pit |  |  | 42 | 50 | 30000
| Cellat Pit/Slab/Flowline trench |  |  | 232 | 339 | 240000
| Perimeter Drains |  |  | 93 | 93 | 80000
| Fencing |  |  | 81 | 123 | 183000
| Septic Tank/Soakaway |  |  | 17 | 30 | 24000

## VSMDATA_EQP
NO | ACTIVITY | DESCRIPTION | VATmins | PLTmins | VATdays | PLTdays | Costs
1 | PreMob-PO | ISSUE PO | 5 | 6720 | 0.010417 | 14
2 | PreMob-HSE1 | Contractor submit HSE, JHA plan | 5 | 10080 | 0.010417 | 21
3 | PreMob-HSE2 | Proj Eng review HSE plan | 0 | 0 | 0 | 0
4 | PreMob-HSE3 | HSE Adv review HSE plan | 0 | 0 | 0 | 0
5 | PreMob-HSE4 | Contract Holder review plan | 0 | 0 | 0 | 0
6 | PreMob-HSE5 | Contract Owner review plan | 0 | 0 | 0 | 0
7 | PreMob-HSE6 | Hold Challenge session | 0 | 0 | 0 | 7
8 | PreMob-EQ1 | Contractor Submit Equipment list | 5 | 6720 | 0.010417 | 14
9 | PreMob-EQ2 | Send Equip list to Logistics | 5 | 158.4 | 0.010417 | 0.33
10 | PreMob-EQ3 | Inspect Equipment (Premob) | 960 | 13440 | 2 | 28
11 | PreMob-SEC1 | Contractor submit Security plan | 0 | 0 | 0 | 0
12 | PreMob-SEC2 | Send Security plan to ASA | 0 | 0 | 0 | 0
13 | PreMob-SEC3 | Approve Security plan | 0 | 0 | 0 | 0
14 | PreMob-FTO | Obtain FTO | 0 | 0 | 0 | 0
15 | PreMob-HSE7 | Issue Premob Cert | 5 | 16800 | 0.010417 | 35
16 | PreMob-TRN1 | Contractor move EQP/PERS to site | 1440 | 6720 | 3 | 14 | 300000
17 | PreMob-HSE8 | Conduct HSE Induction | 480 | 3360 | 1 | 7
18 | PreMob-OFF | Set up Site office | 0 | 0 | 0 | 0
19 | PreMob-MED | Medical Certification | 480 | 4800 | 1 | 10
20 | Bush Clearing | Bush Clearing | 3360 | 4800 | 7 | 10 | 20000
21 | Stripping | Stripping | 2400 | 3360 | 5 | 7 | 95000
22 | SandFilling | SandFilling | 13440 | 26880 | 28 | 56 | 700000
23 | ConcreteWorks1 | Hardcore | 0 | 0 | 0 | 0
24 | ConcreteWorks2 | Excavation | 0 | 0 | 0 | 0
25 | ConcreteWorks3 | Blinding | 0 | 0 | 0 | 0
26 | ConcreteWorks4 | Reinforcement Fixing | 0 | 0 | 0 | 0
27 | ConcreteWorks5 | Formwok | 0 | 0 | 0 | 0
28 | ConcreteWorks6 | Concrete Casting | 0 | 0 | 0 | 0
29 | ConcreteWorks7 | Curing | 0 | 0 | 0 | 0
30 | ConcreteSlabs1 | Waste Pit | 35520 | 71520 | 74 | 149 | 130000
31 | ConcreteSlabs2 | Gen Slab | 26400 | 39840 | 55 | 83 | 100000
32 | ConcreteSlabs3 | Mud Tank | 39360 | 39360 | 82 | 82 | 230000
33 | ConcreteSlabs4 | Cement Slab | 16800 | 20160 | 35 | 42 | 20000
34 | ConcreteSlabs5 | Evacuation Pit | 20160 | 24000 | 42 | 50 | 30000
35 | ConcreteSlabs6 | Cellat Pit/Slab/Flowline trench | 111360 | 162720 | 232 | 339 | 240000
36 | ConcreteSlabs7 | Perimeter Drains | 44640 | 44640 | 93 | 93 | 80000
37 | ConcreteSlabs8 | Fencing | 38880 | 59040 | 81 | 123 | 183000
38 | ConcreteSlabs9 | Septic Tank/Soakaway | 8160 | 14400 | 17 | 30 | 24000
39 | CementStab | Cement Slab | 3360 | 6720 | 7 | 14 | 138000
40 | BaseCourse | Base Course | 2400 | 13440 | 5 | 28 | 300000
41 | AshpaltSurf1 | MC1 | 960 | 4800 | 2 | 10 | 20000
42 | AshpaltSurf2 | Colas | 3360 | 1612800 | 7 | 3360 | 17000
43 | AshpaltSurf3 | Apply Ashpalt wearing course | 3360 | 13440 | 7 | 28 | 197000
44 | DEMOB1 | Clean Site | 3360 | 6720 | 7 | 14
45 | DEMOB2 | Remove EQP/PERS from site | 3360 | 6720 | 7 | 14 | 293000
46 | PreparedLoc | Prepared Location | 0 | 0 | 0 | 0 | 0

## VSMDATA_HSE
NO | ACTIVITY | DESCRIPTION | VATmins | PLTmins | VATdays | PLTdays | Costs
1 | PreMob-PO | ISSUE PO | 5 | 6720 | 0.010417 | 14
2 | PreMob-HSE1 | Contractor submit HSE, JHA plan | 5 | 10080 | 0.010417 | 21
3 | PreMob-HSE2 | Proj Eng review HSE plan | 480 | 1440 | 1 | 3
4 | PreMob-HSE3 | HSE Adv review HSE plan | 480 | 1440 | 1 | 3
5 | PreMob-HSE4 | Contract Holder review plan | 480 | 1920 | 1 | 4
6 | PreMob-HSE5 | Contract Owner review plan | 480 | 3360 | 1 | 7
7 | PreMob-HSE6 | Hold Challenge session | 480 | 3360 | 1 | 7
8 | PreMob-EQ1 | Contractor Submit Equipment list | 0 | 0 | 0 | 0
9 | PreMob-EQ2 | Send Equip list to Logistics | 0 | 0 | 0 | 0
10 | PreMob-EQ3 | Inspect Equipment (Premob) | 0 | 0 | 0 | 0
11 | PreMob-SEC1 | Contractor submit Security plan | 0 | 0 | 0 | 0
12 | PreMob-SEC2 | Send Security plan to ASA | 0 | 0 | 0 | 0
13 | PreMob-SEC3 | Approve Security plan | 0 | 0 | 0 | 0
14 | PreMob-FTO | Obtain FTO | 0 | 0 | 0 | 0
15 | PreMob-HSE7 | Issue Premob Cert | 5 | 16800 | 0.010417 | 35
16 | PreMob-TRN1 | Contractor move EQP/PERS to site | 1440 | 6720 | 3 | 14 | 300000
17 | PreMob-HSE8 | Conduct HSE Induction | 480 | 3360 | 1 | 7
18 | PreMob-OFF | Set up Site office | 0 | 0 | 0 | 0
19 | PreMob-MED | Medical Certification | 480 | 4800 | 1 | 10
20 | Bush Clearing | Bush Clearing | 3360 | 4800 | 7 | 10 | 20000
21 | Stripping | Stripping | 2400 | 3360 | 5 | 7 | 95000
22 | SandFilling | SandFilling | 13440 | 26880 | 28 | 56 | 700000
23 | ConcreteWorks1 | Hardcore | 0 | 0 | 0 | 0
24 | ConcreteWorks2 | Excavation | 0 | 0 | 0 | 0
25 | ConcreteWorks3 | Blinding | 0 | 0 | 0 | 0
26 | ConcreteWorks4 | Reinforcement Fixing | 0 | 0 | 0 | 0
27 | ConcreteWorks5 | Formwok | 0 | 0 | 0 | 0
28 | ConcreteWorks6 | Concrete Casting | 0 | 0 | 0 | 0
29 | ConcreteWorks7 | Curing | 0 | 0 | 0 | 0
30 | ConcreteSlabs1 | Waste Pit | 35520 | 71520 | 74 | 149 | 130000
31 | ConcreteSlabs2 | Gen Slab | 26400 | 39840 | 55 | 83 | 100000
32 | ConcreteSlabs3 | Mud Tank | 39360 | 39360 | 82 | 82 | 230000
33 | ConcreteSlabs4 | Cement Slab | 16800 | 20160 | 35 | 42 | 20000
34 | ConcreteSlabs5 | Evacuation Pit | 20160 | 24000 | 42 | 50 | 30000
35 | ConcreteSlabs6 | Cellat Pit/Slab/Flowline trench | 0 | 0 | 0 | 0 | 240000
36 | ConcreteSlabs7 | Perimeter Drains | 44640 | 44640 | 93 | 93 | 80000
37 | ConcreteSlabs8 | Fencing | 38880 | 59040 | 81 | 123 | 183000
38 | ConcreteSlabs9 | Septic Tank/Soakaway | 8160 | 14400 | 17 | 30 | 24000
39 | CementStab | Cement Slab | 3360 | 6720 | 7 | 14 | 138000
40 | BaseCourse | Base Course | 2400 | 13440 | 5 | 28 | 300000
41 | AshpaltSurf1 | MC1 | 960 | 4800 | 2 | 10 | 20000
42 | AshpaltSurf2 | Colas | 3360 | 1612800 | 7 | 3360 | 17000
43 | AshpaltSurf3 | Apply Ashpalt wearing course | 3360 | 13440 | 7 | 28 | 197000
44 | DEMOB1 | Clean Site | 3360 | 6720 | 7 | 14
45 | DEMOB2 | Remove EQP/PERS from site | 3360 | 6720 | 7 | 14 | 293000
46 | PreparedLoc | Prepared Location | 0 | 0 | 0 | 0 | 0
Mins |  |  | 274095 | 2072640 | 571.0312 | 4318
Hours |  |  | 4568.25 | 34544
Days |  |  | 571.0312 | 4318
Months |  |  | 25.956 | 196.2727

## Premob
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43
ISSUE PO | bar: 1 to 14
Contractor submit HSE, JHA plan | bar: 1 to 21
Proj Eng review HSE plan | bar: 1 to 3
HSE Adv review HSE plan | bar: 1 to 3
Contract Holder review plan | bar: 1 to 5
Contract Owner review plan | bar: 1 to 8
Hold Challenge session | bar: 1 to 8
Contractor Submit Equipment list | bar: 1 to 14
Send Equip list to Logistics | bar: 1
Inspect Equipment (Premob) | bar: 1 to 30
Contractor submit Security plan | bar: 1 to 7
Send Security plan to ASA | bar: 1
Approve Security plan | bar: 1 to 21
Obtain FTO
Issue Premob Cert | bar: 1 to 35
Contractor move EQP/PERS to site | bar: 1 to 17
Conduct HSE Induction | bar: 1 to 8
Set up Site office | bar: 1 to 8
Medical Certification | bar: 1 to 11
PreMob-PO | ISSUE PO | 1: 5; 2: 6720; 3: 0.010417; 4: 14; 5: 14.0104
PreMob-HSE1 | Contractor submit HSE, JHA plan | 1: 5; 2: 10080; 3: 0.010417; 4: 21; 5: 21.0104
PreMob-HSE2 | Proj Eng review HSE plan | 1: 480; 2: 1440; 3: 1; 4: 3; 5: 4
PreMob-HSE3 | HSE Adv review HSE plan | 1: 480; 2: 1440; 3: 1; 4: 3; 5: 4
PreMob-HSE4 | Contract Holder review plan | 1: 480; 2: 1920; 3: 1; 4: 4; 5: 5
PreMob-HSE5 | Contract Owner review plan | 1: 480; 2: 3360; 3: 1; 4: 7; 5: 8
PreMob-HSE6 | Hold Challenge session | 1: 480; 2: 3360; 3: 1; 4: 7; 5: 8
PreMob-EQ1 | Contractor Submit Equipment list | 1: 5; 2: 6720; 3: 0.010417; 4: 14; 5: 14.0104
PreMob-EQ2 | Send Equip list to Logistics | 1: 5; 2: 158.4; 3: 0.010417; 4: 0.33; 5: 0.34042
PreMob-EQ3 | Inspect Equipment (Premob) | 1: 960; 2: 13440; 3: 2; 4: 28; 5: 30
PreMob-SEC1 | Contractor submit Security plan | 1: 5; 2: 3360; 3: 0.010417; 4: 7; 5: 7.0104
PreMob-SEC2 | Send Security plan to ASA | 1: 5; 2: 0; 3: 0.010417; 5: 0.010417
PreMob-SEC3 | Approve Security plan | 1: 2; 2: 10080; 3: 0.0041667; 4: 21; 5: 21.0042
PreMob-FTO | Obtain FTO | 1: 480; 2: 20160; 3: 1; 4: 42; 5: 43
PreMob-HSE7 | Issue Premob Cert | 1: 5; 2: 16800; 3: 0.010417; 4: 35; 5: 35.0104
PreMob-TRN1 | Contractor move EQP/PERS to site | 1: 1440; 2: 6720; 3: 3; 4: 14; 5: 17
PreMob-HSE8 | Conduct HSE Induction | 1: 480; 2: 3360; 3: 1; 4: 7; 5: 8
PreMob-OFF | Set up Site office | 1: 480; 2: 3360; 3: 1; 4: 7; 5: 8
PreMob-MED | Medical Certification | 1: 480; 2: 4800; 3: 1; 4: 10; 5: 11

## WORKED VERSION
NO | ACTIVITY | DESCRIPTION | VATmins | PLTmins | VATdays | PLTdays | Month | Costs | VATdays | PLTdays | VAT+PLT2 | VAT+PLT | VATdays | PLTdays | VAT+PLT2
1 | PreMob-PO | ISSUE PO | [8 empty] | 0 | 0 |  |  | 0
2 | PreMob-HSE1 | Contractor submit HSE, JHA plan | [8 empty] | 0 | 0 |  |  | 0
3 | PreMob-HSE2 | Proj Eng review HSE plan | [8 empty] | 0 | 0 |  |  | 0
4 | PreMob-HSE3 | HSE Adv review HSE plan | [8 empty] | 0 | 0 |  |  | 0
5 | PreMob-HSE4 | Contract Holder review plan | [8 empty] | 0 | 0 |  |  | 0
6 | PreMob-HSE5 | Contract Owner review plan | [8 empty] | 0 | 0 |  |  | 0
7 | PreMob-HSE6 | Hold Challenge session | [8 empty] | 0 | 0 |  |  | 0
8 | PreMob-EQ1 | Contractor Submit Equipment list | [8 empty] | 0 | 0 |  |  | 0
9 | PreMob-EQ2 | Send Equip list to Logistics | [8 empty] | 0 | 0 |  |  | 0
10 | PreMob-EQ3 | Inspect Equipment (Premob) | [8 empty] | 0 | 0 |  |  | 0
11 | PreMob-SEC1 | Contractor submit Security plan | [8 empty] | 0 | 0 |  |  | 0
12 | PreMob-SEC2 | Send Security plan to ASA | [8 empty] | 0 | 0 |  |  | 0
13 | PreMob-SEC3 | Approve Security plan | [8 empty] | 0 | 0 |  |  | 0
14 | PreMob-FTO | Obtain FTO | 480 | 20160 | 1 | 42 | 1.9091 |  | 1 | 42 | 43 | 43 | 1 | 42 | 43
15 | PreMob-HSE7 | Issue Premob Cert | 5 | 10 | 0.010417 | 0 | 0 |  | 0.010417 | 1 | 0.010417 | 0.010417 | 0.010417 | 0 | 0.010417
16 | PreMob-TRN1 | Contractor move EQP/PERS to site | 1440 | 6720 | 3 | 14 | 0.63636 | 300000 | 3 | 14 | 17 | 17 | 3 | 14 | 17
17 | PreMob-HSE8 | Conduct HSE Induction | [8 empty] | 0 | 0 |  |  | 0
18 | PreMob-OFF | Set up Site office | [8 empty] | 0 | 0 |  |  | 0
19 | PreMob-MED | Medical Certification | 480 | 4800 | 1 | 10 | 0.45455 |  | 1 | 10 | 11 | 11 | 1 | 10 | 11
[11 empty] | 0 | 0 |  |  | 0
20 | Bush Clearing | Bush Clearing | 3360 | 4800 | 7 | 10 | 0.45455 | 20000 | 7 | 10 | 17 | 17 | 7 | 10 | 17
21 | Stripping | Stripping | 2400 | 3360 | 5 | 7 | 0.31818 | 95000 | 5 | 7 | 12 | 12 | 5 | 7 | 12
22 | SandFilling | SandFilling | 13440 | 26880 | 18 | 56 | 2.5455 | 700000 | 18 | 56 | 74 | 74 | 15 | 25 | 40
[10 empty] | 0 | 0 | 0 |  | 0 | 0
30 | ConcreteSlabs1 | Waste Pit | 35520 | 71520 | 74 | 149 | 6.7727 | 130000 | 15 | 51 | 66 | 223 | 0 | 0 | 0
39 | CementStab | Cement Slab | 3360 | 6720 | 7 | 14 | 0.63636 | 138000 | 3 | 18 | 21 | 21 | 0 | 0 | 0
31 | ConcreteSlabs2 | Gen Slab | 26400 | 39840 | 55 | 83 | 3.7727 | 100000 | 6 | 34 | 40 | 138 | 0 | 0 | 0
32 | ConcreteSlabs3 | Mud Tank | 39360 | 39360 | 82 | 82 | 3.7273 | 230000 | 14 | 66 | 80 | 164 | 0 | 0 | 0
34 | ConcreteSlabs5 | Evacuation Pit | 20160 | 24000 | 42 | 50 | 2.2727 | 30000 | 6 | 12 | 18 | 92 | 0 | 0 | 0
35 | ConcreteSlabs6 | Cellat Pit/Slab | 111360 | 162720 | 232 | 339 | 15.4091 | 240000 | 10 | 72 | 82 | 571 | 0 | 0 | 0
|  | Flowline trench | [6 empty] | 8 | 36 | 44 |  | 0 | 0 | 0
36 | ConcreteSlabs7 | Perimeter Drains | 44640 | 44640 | 93 | 93 | 4.2273 | 80000 | 7 | 23 | 30 | 186 | 0 | 0 | 0
37 | ConcreteSlabs8 | Fencing | 38880 | 59040 | 81 | 123 | 5.5909 | 183000 | 35 | 53 | 88 | 204 | 35 | 53 | 88
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
| AshpaltSurf1 | Cement Stabilisation | [5 empty] | 91893 | 2 | 14 | 16 |  | 2 | 14 | 16
| AshpaltSurf2 | Crushed Rock Base | [5 empty] | 165365 | 1 | 13 | 14 |  | 1 | 13 | 14
41 | AshpaltSurf3 | MC1 | 960 | 4800 | 2 | 10 | 0.45455 | 20000 | 2 | 10 | 12 | 12 | 2 | 10 | 12
42 | AshpaltSurf4 | Colas | [7 empty] | 0 | 0 | 0 |  | 0 | 0
43 | AshpaltSurf5 | Apply Ashpalt wearing course | 3360 | 9600 | 7 | 20 | 0.90909 | 197000 | 7 | 20 | 27 | 27 | 7 | 20 | 27 | 12 | 57
[10 empty] | 0 | 0 | 0 |  | 0 | 0
44 | DEMOB1 | Clean Site | [7 empty] | 0 | 0 | 0 |  | 0 | 0
45 | DEMOB2 | Remove EQP/PERS from site | 3360 | 6720 | 7 | 14 | 0.63636 | 293000 | 3 | 12 | 15 | 21 | 3 | 12 | 15
46 | PreparedLoc | Prepared Location | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mins |  |  | 348965 | 535690 | 717.0104 | 1116 |  | 3013258
Hours |  |  | 5816.0833 | 8928.1667
Days |  |  | 727.0104 | 1116.0208 | [8 empty] | 82.0104 | 230 | 312.0104
Months |  |  | 33.0459 | 50.7282 |  |  | 50.7273 |  |  |  |  | 1833.0104 | 3.7277 | 10.4545 | 14.1823
0.35657
35.6567
|  |  | month | workday | minutes
|  |  | 8 | 176
|  |  | 18 | 396

## IMPROVEMENTS
NO | ACTIVITY | DESCRIPTION | VATmins | PLTmins | VATdays | PLTdays | Month | Costs
1 | PreMob-PO | ISSUE PO | 5 | 6720 | 0.010417 | 14 | 0.63636
2 | PreMob-HSE1 | Contractor submit HSE, JHA plan | 5 | 10080 | 0.010417 | 21 | 0.95455
3 | PreMob-HSE2 | Proj Eng review HSE plan | 480 | 1440 | 1 | 3 | 0.13636
4 | PreMob-HSE3 | HSE Adv review HSE plan | 480 | 1440 | 1 | 3 | 0.13636
5 | PreMob-HSE4 | Contract Holder review plan | 480 | 1920 | 1 | 4 | 0.18182
6 | PreMob-HSE5 | Contract Owner review plan | 480 | 3360 | 1 | 7 | 0.31818
7 | PreMob-HSE6 | Hold Challenge session | 480 | 3360 | 1 | 7 | 0.31818
Mins |  |  | 2405 | 21600 |  |  |  | Mins
Hrs |  |  | 40.0833 | 360 |  |  |  | Hrs
Days |  |  | 5.0104 | 45 | 5.0104 | 45 |  | Days
Month |  |  | 0.22775 | 2.0455 |  |  | 2.0455 | Mnths
8 | PreMob-EQ1 | Contractor Submit Equipment list | 5 | 6720 | 0.010417 | 14 | 0.63636
9 | PreMob-EQ2 | Send Equip list to Logistics | 5 | 158.4 | 0.010417 | 0.33 | 0.015
10 | PreMob-EQ3 | Inspect Equipment (Premob) | 960 | 13440 | 2 | 28 | 1.2727
Mins |  |  | 970 | 20318.4 |  |  |  | Mins
Hrs |  |  | 16.1667 | 338.64 |  |  |  | Hrs
Days |  |  | 2.0208 | 42.33 | 2.0208 | 42.33 |  | Days
Month |  |  |  | 1.9241 |  | 1.9241 | 1.9241 | Mnths
11 | PreMob-SEC1 | Contractor submit Security plan | 5 | 3360 | 0.010417 | 7 | 0.31818
12 | PreMob-SEC2 | Send Security plan to ASA | 5 | 10 | 0.010417 | 0.020833 | 0.00094697
13 | PreMob-SEC3 | Approve Security plan | 2 | 10080 | 0.0041667 | 21 | 0.95455
Mins |  |  | 12 | 13450 |  |  |  | Mins
Hrs |  |  | 0.2 | 224.1667 |  |  |  | Hrs
Days |  |  | 0.025 | 28.0208 | 0.025 | 28.0208 |  | Days
Month |  |  | 0.0011364 | 1.2737 |  | 1.2737 | 1.2737 | Mnths
14 | PreMob-FTO | Obtain FTO | 480 | 20160 | 1 | 42 | 1.9091
Mins |  |  | 480.0011 | 20161.2737 |  |  |  | Mins
Hrs |  |  | 8 | 336.0212 |  |  |  | Hrs
Days |  |  | 1 | 42.0027 | 1 | 42 |  | Days
Month |  |  | 0.045455 | 1.9092 |  | 1.9091 | 1.9091 | Mnths
15 | PreMob-HSE7 | Issue Premob Cert | 5 | 16800 | 0.010417 | 35 | 1.5909
16 | PreMob-TRN1 | Contractor move EQP/PERS to site | 1440 | 6720 | 3 | 14 | 0.63636 | 300000
17 | PreMob-HSE8 | Conduct HSE Induction | 480 | 3360 | 1 | 7 | 0.31818
18 | PreMob-OFF | Set up Site office | 480 | 3360 | 1 | 7 | 0.31818
19 | PreMob-MED | Medical Certification | 480 | 4800 | 1 | 10 | 0.45455
20 | Bush Clearing | Bush Clearing | 3360 | 4800 | 7 | 10 | 0.45455 | 20000
21 | Stripping | Stripping | 2400 | 3360 | 5 | 7 | 0.31818 | 95000
22 | SandFilling | SandFilling | 13440 | 26880 | 28 | 56 | 2.5455 | 700000
30 | ConcreteSlabs1 | Waste Pit | 35520 | 71520 | 74 | 149 | 6.7727 | 130000
31 | ConcreteSlabs2 | Gen Slab | 26400 | 39840 | 55 | 83 | 3.7727 | 100000
32 | ConcreteSlabs3 | Mud Tank | 39360 | 39360 | 82 | 82 | 3.7273 | 230000
33 | ConcreteSlabs4 | Cement Slab | 16800 | 20160 | 35 | 42 | 1.9091 | 20000
34 | ConcreteSlabs5 | Evacuation Pit | 20160 | 24000 | 42 | 50 | 2.2727 | 30000
35 | ConcreteSlabs6 | Cellat Pit/Slab/Flowline trench | 111360 | 162720 | 232 | 339 | 15.4091 | 240000
36 | ConcreteSlabs7 | Perimeter Drains | 44640 | 44640 | 93 | 93 | 4.2273 | 80000
37 | ConcreteSlabs8 | Fencing | 38880 | 59040 | 81 | 123 | 5.5909 | 183000
38 | ConcreteSlabs9 | Septic Tank/Soakaway | 8160 | 14400 | 17 | 30 | 1.3636 | 24000
39 | CementStab | Cement Slab | 3360 | 6720 | 7 | 14 | 0.63636 | 138000
40 | BaseCourse | Base Course | 2400 | 13440 | 5 | 28 | 1.2727 | 300000
41 | AshpaltSurf1 | MC1 | 960 | 4800 | 2 | 10 | 0.45455 | 20000
42 | AshpaltSurf2 | Colas | 3360 | 1612800 | 7 | 3360 | 152.7273 | 17000
43 | AshpaltSurf3 | Apply Ashpalt wearing course | 3360 | 13440 | 7 | 28 | 1.2727 | 197000
44 | DEMOB1 | Clean Site | 3360 | 6720 | 7 | 14 | 0.63636
45 | DEMOB2 | Remove EQP/PERS from site | 3360 | 6720 | 7 | 14 | 0.63636 | 293000
46 | PreparedLoc | Prepared Location | 0 | 0 | 0 | 0 | 0 | 0
Mins |  |  | 391336.7817 | 2369601.4075 | 815.1333 | 4938.8085 |  | 3117000
Hours |  |  | 6522.2797 | 39493.3568
Days |  |  | 815.285 | 4936.6696
Months |  |  | 37.0584 | 224.3941 |  |  | 224.2592

## IMPROVEMENTS 2
|  |  |  | All processes Including parallel Processes |  |  |  | For Cycle time Calculations (Paralell activities have been removed) |  |  | Improvemnets
NO | ACTIVITY | DESCRIPTION | Costs F$ | VATdays | PLTdays | VAT+PLT2 |  | VATdays | PLTdays | VAT+PLT2 | VATdays | PLTdays | VAT+PLT2 | Cost |  | Lean Action
1 | PreMob-PO | ISSUE PO |  | 0.010417 | 14 | 14.0104 |  |  |  | 0 | 0.010417 | 14 | 14.0104
2 | PreMob-HSE1 | Contractor submit HSE, JHA plan |  | 0.010417 | 21 | 21.0104 |  |  |  | 0 | 0.010417 | 5 | 5.0104 |  |  | Standard Work/Quality in Station
3 | PreMob-HSE2 | Proj Eng review HSE plan |  | 1 | 3 | 4 |  |  |  | 0 | 0 | 0 | 0 |  |  | Activity
4 | PreMob-HSE3 | HSE Adv review HSE plan |  | 1 | 3 | 4 |  |  |  | 0 | 0.5 | 1 | 1.5 |  |  | Standard Work/Quality in Station
5 | PreMob-HSE4 | Contract Holder review plan |  | 1 | 4 | 5 |  |  |  | 0 | 0 | 0 | 0 |  |  | Standard Work/Quality in Station
6 | PreMob-HSE5 | Contract Owner review plan |  | 1 | 7 | 8 |  |  |  | 0 | 0.5 | 1 | 1.5 |  |  | Discontinue process
7 | PreMob-HSE6 | Hold Challenge session |  | 1 | 7 | 8 | 50.0104 |  |  | 0 | 0 | 0 | 0 |  | 10.0208 | Discontinue process | 39.9896
8 | PreMob-EQ1 | Contractor Submit Equipment list |  | 0.010417 | 14 | 14.0104 |  |  |  | 0 | 0.010417 | 2 | 2.0104 |  |  | Standard Work/Quality in Station
9 | PreMob-EQ2 | Send Equip list to Logistics |  | 0.010417 | 0.33 | 0.34042 |  |  |  | 0 | 0.010417 | 0.33 | 0.34042
10 | PreMob-EQ3 | Inspect Equipment (Premob) |  | 2 | 28 | 30 | 44.3508 |  |  | 0 | 2 | 5 | 7 |  | 9.3508 | Standard Work/Quality in Station/Full Delegation/Full process review | 35
11 | PreMob-SEC1 | Contractor submit Security plan |  | 0.010417 | 7 | 7.0104 |  |  |  | 0 | 0.010417 | 2 | 2.0104 |  |  | Standard Work/Quality in Station
12 | PreMob-SEC2 | Send Security plan to ASA |  | 0.010417 | 0.020833 | 0.03125 |  |  |  | 0 | 0.010417 | 0.020833 | 0.03125
13 | PreMob-SEC3 | Approve Security plan |  | 0.0041667 | 21 | 21.0042 |  |  |  | 0 | 0.0041667 | 5 | 5.0042 |  |  | Standard Work/Quality in Station/Full Delegation/Full process review
14 | PreMob-FTO | Obtain FTO |  | 1 | 42 | 43 |  | 1 | 42 | 43 | 1 | 29 | 30 |  |  | Standard Work/Quality in Station/Full Delegation/Full process review
15 | PreMob-HSE7 | Issue Premob Cert |  | 0.010417 | 1 | 1.0104 |  | 0.010417 | 0 | 0.010417 | 0.010417 | 1 | 1.0104
16 | PreMob-TRN1 | Contractor move EQP/PERS to site | 300000 | 3 | 14 | 17 |  | 3 | 14 | 17 | 3 | 14 | 17 | 300000
17 | PreMob-HSE8 | Conduct HSE Induction |  | 1 | 7 | 8 |  |  |  | 0 | 0 | 0 | 0
18 | PreMob-OFF | Set up Site office |  | 1 | 7 | 8 |  |  |  | 0 | 0 | 0 | 0
19 | PreMob-MED | Medical Certification |  | 1 | 10 | 11 |  | 1 | 10 | 11 | 1 | 10 | 11
20 | Bush Clearing | Bush Clearing | 20000 | 7 | 10 | 17 |  | 7 | 10 | 17 | 7 | 10 | 17 | 20000
21 | Stripping | Stripping | 95000 | 5 | 7 | 12 |  | 5 | 7 | 12 | 5 | 7 | 12 | 95000
22 | SandFilling | SandFilling | 700000 | 15 | 25 | 40 |  | 15 | 25 | 40 | 15 | 10 | 25 | 700000 |  | Source sand from proximate locations
23 | ConcreteSlabs1 | Waste Pit | 130000 | 15 | 51 | 66 |  | 0 | 0 | 0 |  |  |  | 130000 |  | Evaluate precast concrete/Form work Eliminate waste pit - to calculate cost benefit Elimnate or reduce Generator Slab Re-evaluate slabs from DPR regulation of containments and avoiding seepage
24 | CementStab | Cement Slab | 138000 | 3 | 18 | 21 |  | 0 | 0 | 0 |  |  |  | 138000
25 | ConcreteSlabs2 | Gen Slab | 100000 | 6 | 34 | 40 |  | 0 | 0 | 0 |  |  |  | 100000
26 | ConcreteSlabs3 | Mud Tank | 230000 | 14 | 66 | 80 |  | 0 | 0 | 0 |  |  |  | 230000
27 | ConcreteSlabs5 | Evacuation Pit | 30000 | 6 | 12 | 18 |  | 0 | 0 | 0 |  |  |  | 30000
28 | ConcreteSlabs6 | Cellat Pit/Slab | 240000 | 10 | 72 | 82 |  | 0 | 0 | 0 |  |  |  | 240000
29 | ConcreteSlabs7 | Flowline trench |  | 8 | 36 | 44 |  | 0 | 0 | 0
30 | ConcreteSlabs7 | Perimeter Drains | 80000 | 7 | 23 | 30 |  | 0 | 0 | 0 |  |  |  | 80000
31 | ConcreteSlabs8 | Fencing | 183000 | 35 | 53 | 88 |  | 35 | 53 | 88 | 8 | 22 | 30 | 183000
32 | AshpaltSurf1 | Cement Stabilisation | 91893 | 2 | 14 | 16 |  | 2 | 14 | 16 | 0 | 0 | 0 | 91893 |  | Implement Durabase Mat tech
33 | AshpaltSurf2 | Crushed Rock Base | 165365 | 1 | 13 | 14 |  | 1 | 13 | 14 | 0 | 0 | 0 | 165365
34 | AshpaltSurf3 | MC1 | 20000 | 2 | 10 | 12 |  | 2 | 10 | 12 | 2 | 0 | 0 | 20000
35 | AshpaltSurf4 | Colas |  | 2 | 10 | 12 |  |  | 0 | 0 | 0 | 0 | 0
36 | AshpaltSurf5 | Apply Ashpalt wearing course | 197000 | 7 | 20 | 27 |  | 7 | 20 | 27 | 4 | 12 | 16 | 197000
37 | DEMOB1 | Clean Site |  | 7 | 14 | 21 |  |  | 0 | 0 | 0 | 0 | 0
38 | DEMOB2 | Remove EQP/PERS from site | 293000 | 3 | 12 | 15 |  | 3 | 12 | 15 | 3 | 12 | 15 | 293000
39 | PreparedLoc | Prepared Location | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Costs |  |  | 3013258
Mins
Hours
Days | [7 empty] | 82.0104 | 230 | 312.0104 | 52.0771 | 162.3508 | 212.4279 | 3013258
Months | [7 empty] | 3.1542 | 8.8462 | 12.0004 | 2.003 | 6.2443 | 8.1703
Note workdays = 26days/month

## TO PLOT FINAL
NO | ACTIVITY | DESCRIPTION | Costs F$ | VATdays | PLTdays | VAT+PLT2
1 | PreMob-PO | ISSUE PO |  | 0.010417 | 14 | 14.0104
2 | PreMob-HSE1 | Contractor submit HSE, JHA plan |  | 0.010417 | 21 | 21.0104
3 | PreMob-HSE2 | Proj Eng review HSE plan |  | 1 | 3 | 4
4 | PreMob-HSE3 | HSE Adv review HSE plan |  | 1 | 3 | 4
5 | PreMob-HSE4 | Contract Holder review plan |  | 1 | 4 | 5
6 | PreMob-HSE5 | Contract Owner review plan |  | 1 | 7 | 8
7 | PreMob-HSE6 | Hold Challenge session |  | 1 | 7 | 8
8 | PreMob-EQ1 | Contractor Submit Equipment list to Contract holder |  | 0.010417 | 14 | 14.0104
9 | PreMob-EQ2 | Contract Holder Send Equip list to Premob Admin |  | 0.010417 | 0.33 | 0.34042
10 | PreMob-EQ3 | Adim send list to Premob Inspector |  | 0.01 | 1 | 1.01
11 | PreMob-EQ4 | Inspector informs Contractholder of inspection date |  | 0.01 | 1 | 1.01
12 | PreMob-EQ5 | Contract holder agrees? |  | 0.01 | 1 | 1.01
13 | PreMob-EQ6 | Premob Inspector allocates inspector |  | 0.01 | 1 | 1.01
14 | PreMob-EQ7 | Admin arranges Vehicle |  | 0.5 | 1 | 1.5
15 | PreMob-EQ8 | Inspector Prepares for journey |  | 0.5 | 1 | 1.5
16 | PreMob-EQ9 | Inspector travels to location with Request
17 | PreMob-EQ10 | Inspector carry out Premob inspection |  | 1 | 3 | 4
18 | PreMob-EQ11 | Documents OK/Passed?
19 | PreMob-EQ12 | Release result/Sicker 2days |  | 0.01 | 2 | 2.01
20 | PreMob-EQ13 | Not ok - Prepare fault Notice 48hrs |  | 0.5 | 2 | 2.5
21 | PreMob-EQ14 | Send fault notice to Contract Holder |  | 0.01 | 1 | 1.01
22 | PreMob-EQ15 | Is fault repaired within 10 days?? |  | 1 | 10 | 11
23 | PreMob-EQ16 | Yes Carry Out premob inspection |  | 0.5 | 2 | 2.5 | 30.4004
24 | PreMob-EQ17 | No - fault not repaired within 10 days start afresh
25 | PreMob-SEC1 | Contractor submit Security plan to contract holder |  | 0.010417 | 7 | 7.0104
26 | PreMob-SEC2 | Contract holder sends Security plan to ASA for approval |  | 0.010417 | 0.020833 | 0.03125
27 | PreMob-SEC3 | SAS Reviews Doucmentation Ok? |  | 0.5 | 4 | 4.5
28 | PreMob-SEC4 | YES -ASA sends plan to contract holder to print for signature |  | 0.01 | 3 | 3.01
29 | PreMob-SEC5 | Contractor Signs document |  | 0.01 | 2 | 2.01
30 | PreMob-SEC6 | Contract holder signs document |  | 0.01 | 2 | 2.01
31 | PreMob-SEC7 | ASA signs document |  | 0.01 | 1 | 1.01
32 | PreMob-SEC3 | Security Mgr Approve Security plan |  | 0.0041667 | 2 | 2.0042
33 | PreMob-SEC9 | NO - ASA send document to contract holder |  | 0.01 | 1 | 1.01
34 | PreMob-SEC10 | Contract holders send document to contrtactor for rework |  | 0.01 | 2 | 2.01
35 | PreMob-SEC11 | Contractor reworks security plan and resubmits |  | 0.5 | 2 | 2.5 | 20.0954
36 | PreMob-FTO | Obtain FTO |  | 1 | 42 | 43
37 | PreMob-HSE7 | Issue Premob Cert |  | 0.010417 | 1 | 1.0104
38 | PreMob-TRN1 | Contractor move EQP/PERS to site | 300000 | 3 | 14 | 17
39 | PreMob-HSE8 | Conduct HSE Induction |  | 1 | 7 | 8
40 | PreMob-OFF | Set up Site office |  | 1 | 7 | 8
41 | PreMob-MED | Medical Certification |  | 1 | 10 | 11
42 | Bush Clearing | Bush Clearing | 20000 | 7 | 10 | 17
43 | Stripping | Stripping | 95000 | 5 | 7 | 12
44 | SandFilling | SandFilling | 700000 | 15 | 25 | 40
45 | ConcreteWorks1 | Hardcore |  | 19 | 62 | 81
46 | ConcreteWorks2 | Excavation |  | 83 | 131 | 214
47 | ConcreteWorks3 | Blinding |  | 46 | 99 | 145
48 | ConcreteWorks4 | Reinforcement Fixing |  | 90 | 150 | 240
49 | ConcreteWorks5 | Formwork |  | 91 | 146 | 237
50 | ConcreteWorks6 | Concrete Casting |  | 116 | 232 | 348
51 | ConcreteWorks7 | Curing |  | 28 | 28 | 56
52 | ConcreteSlabs1 | Waste Pit | 130000 | 15 | 51 | 66
53 | CementSlabs2 | Cement Slab | 138000 | 3 | 18 | 21
54 | ConcreteSlabs3 | Gen Slab | 100000 | 6 | 34 | 40
55 | ConcreteSlabs4 | Mud Tank | 230000 | 14 | 66 | 80
56 | ConcreteSlabs5 | Evacuation Pit | 30000 | 6 | 12 | 18
57 | ConcreteSlabs6 | Cellat Pit/Slab | 240000 | 10 | 72 | 82
58 | ConcreteSlabs7 | Flowline trench |  | 8 | 36 | 44
59 | ConcreteSlabs8 | Perimeter Drains | 80000 | 7 | 23 | 30
60 | ConcreteSlabs9 | Fencing | 183000 | 35 | 53 | 88
61 | AshpaltSurf1 | Cement Stabilisation | 91893 | 2 | 14 | 16
62 | AshpaltSurf2 | Crushed Rock Base | 165365 | 1 | 13 | 14
63 | AshpaltSurf3 | MC1 | 20000 | 2 | 10 | 12
64 | AshpaltSurf4 | Colas |  | 2 | 10 | 12
65 | AshpaltSurf5 | Apply Ashpalt wearing course | 197000 | 7 | 20 | 27
66 | DEMOB1 | Clean Site |  | 7 | 14 | 21
67 | DEMOB2 | Remove EQP/PERS from site | 293000 | 3 | 12 | 15
68 | PreparedLoc | Prepared Location | 0 | 0 | 0 | 0
69 | Durabase Mats | Transport DBM | 9963 | 3 | 6 | 9
70 | Durabase Mats | Lay DBM | 2336 | 1 | 6 | 7
71 | Durabase Mats | Retrieve DBM | 2336 | 5 | 10 | 15

## IMPROVEMENT3_FINAL
|  |  |  | All processes Including parallel Processes |  |  | All processes Including parallel Processes |  |  |  | For Cycle time Calculations (Paralell activities have been removed) |  |  |  | Improvemnets
NO | ACTIVITY | DESCRIPTION | Costs F$ | VATdays | PLTdays | VAT+PLT2 | VATdays | PLTdays | VAT+PLT2 |  | VATdays | PLTdays | VAT+PLT2 |  | VATdays | PLTdays | VAT+PLT2 | TOTAL | SAVINGS | Cost | Lean Action
1 | PreMob-PO | ISSUE PO | 0 | 0.010417 | 14 | 14.0104 | 0.010417 | 14 | 14.0104 | 14 |  |  | 0 |  | 0.010417 | 14 | 14.0104
2 | PreMob-HSE1 | Contractor submit HSE, JHA,Security plan & Equip List |  | 0.010417 | 5 | 5.0104 | 0.010417 | 10 | 10.0104 |  |  |  | 0 |  | 0.010417 | 5 | 5.0104 |  |  |  | Standard Work/Quality in Station
3 | PreMob-HSE2 | Proj Eng review HSE plan |  | 1 | 3 | 4 | 1 | 3 | 4 |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | Activity
4 | PreMob-HSE3 | HSE Adv review HSE plan |  | 1 | 3 | 4 | 1 | 3 | 4 |  |  |  | 0 |  | 0.5 | 1 | 1.5 |  |  |  | Standard Work/Quality in Station
5 | PreMob-HSE4 | Contract Holder review plan |  | 1 | 4 | 5 | 1 | 4 | 5 |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | Standard Work/Quality in Station
6 | PreMob-HSE5 | Contract Owner review plan |  | 1 | 7 | 8 | 1 | 7 | 8 |  |  |  | 0 |  | 0.5 | 1 | 1.5 |  |  |  | Discontinue process
7 | PreMob-HSE6 | Hold Challenge session |  | 1 | 7 | 8 | 1 | 7 | 8 | 39.0104 |  |  | 0 |  | 0 | 0 | 0 | 8.0104 | 31 |  | Discontinue process
8 | PreMob-EQ1 | Contractor Submit Equipment list |  | 0.010417 | 3 | 3.0104 | 0.010417 | 14 | 14.0104 |  |  |  | 0 |  | 0.010417 | 2 | 2.0104 |  |  |  | Standard Work/Quality in Station
9 | PreMob-EQ2 | Send Equip list to Logistics |  | 0.010417 | 0.33 | 0.34042 | 0.010417 | 0.33 | 0.34042 |  |  |  | 0 |  | 0.010417 | 0.33 | 0.34042
10 | PreMob-EQ3 | Inspect Equipment (Premob) |  | 2 | 28 | 30 | 2 | 28 | 30 | 44.3508 |  |  | 0 |  | 2 | 5 | 7 | 9.3508 | 35 |  | Standard Work/Quality in Station/Full Delegation/Full process review
11 | PreMob-SEC1 | Contractor submit Security plan |  | 0.010417 | 4 | 4.0104 | 0.010417 | 7 | 7.0104 |  |  |  | 0 |  | 0.010417 | 2 | 2.0104 |  |  |  | Standard Work/Quality in Station
12 | PreMob-SEC2 | Send Security plan to ASA |  | 0.010417 | 0.020833 | 0.03125 | 0.010417 | 0.020833 | 0.03125 |  |  |  | 0 |  | 0.010417 | 0.020833 | 0.03125
13 | PreMob-SEC3 | Approve Security plan |  | 0.0041667 | 21 | 21.0042 | 0.0041667 | 21 | 21.0042 | 28.0458 |  |  | 0 |  | 0.0041667 | 5 | 5.0042 | 7.0458 | 21 |  | Standard Work/Quality in Station/Full Delegation/Full process review
14 | PreMob-FTO | Obtain FTO |  | 1 | 42 | 43 | 1 | 42 | 43 | 43 | 1 | 42 | 43 |  | 1 | 29 | 30 | 30 | 13 |  | Standard Work/Quality in Station/Full Delegation/Full process review
15 | PreMob-HSE7 | Issue Premob Cert |  | 0.010417 | 1 | 1.0104 | 0.010417 | 1 | 1.0104 |  | 0.010417 | 1 | 0.010417 |  | 0.010417 | 1 | 1.0104
16 | PreMob-TRN1 | Contractor move EQP/PERS to site | 300000 | 3 | 14 | 17 | 3 | 14 | 17 |  | 3 | 14 | 17 |  | 3 | 14 | 17 |  |  | 300000
17 | PreMob-HSE8 | Conduct HSE Induction |  | 1 | 7 | 8 | 1 | 7 | 8 |  |  |  | 0 |  | 0 | 0 | 0
18 | PreMob-OFF | Set up Site office |  | 1 | 7 | 8 | 1 | 7 | 8 |  |  |  | 0 |  | 0 | 0 | 0
19 | PreMob-MED | Medical Certification |  | 1 | 10 | 11 | 1 | 10 | 11 |  | 1 | 10 | 11 |  | 1 | 10 | 11
20 | Bush Clearing | Bush Clearing | 20000 | 7 | 10 | 17 | 7 | 10 | 17 |  | 7 | 10 | 17 |  | 7 | 10 | 17 |  |  | 20000
21 | Stripping | Stripping | 95000 | 5 | 7 | 12 | 5 | 7 | 12 |  | 5 | 7 | 12 |  | 5 | 7 | 12 |  |  | 95000
22 | SandFilling | SandFilling | 700000 | 15 | 25 | 40 | 14 | 24 | 38 |  | 14 | 24 | 38 |  | 15 | 10 | 25 |  |  | 700000 | Source sand from proximate locations
23 | ConcreteSlabs1 | Waste Pit | 130000 | 15 | 51 | 66 | 15 | 51 | 66 |  | 0 | 0 | 0 | [6 empty] | 130000 | Evaluate precast concrete/Form work Eliminate waste pit - to calculate cost benefit Elimnate or reduce Generator Slab Re-evaluate slabs from DPR regulation of containments and avoiding seepage
24 | CementStab | Cement Slab | 138000 | 3 | 18 | 21 | 3 | 18 | 21 |  | 0 | 0 | 0 | [6 empty] | 138000
25 | ConcreteSlabs2 | Gen Slab | 100000 | 6 | 24 | 30 | 6 | 24 | 30 |  | 0 | 0 | 0 | [6 empty] | 100000
26 | ConcreteSlabs3 | Mud Tank | 230000 | 14 | 66 | 80 | 14 | 66 | 80 |  | 0 | 0 | 0 | [6 empty] | 230000
27 | ConcreteSlabs5 | Evacuation Pit | 30000 | 6 | 12 | 18 | 6 | 12 | 18 |  | 0 | 0 | 0 | [6 empty] | 30000
28 | ConcreteSlabs6 | Cellat Pit/Slab | 240000 | 10 | 72 | 82 | 10 | 72 | 82 |  | 0 | 0 | 0 | [6 empty] | 240000
29 | ConcreteSlabs7 | Flowline trench |  | 8 | 24 | 32 | 8 | 24 | 32 |  | 0 | 0 | 0
30 | ConcreteSlabs7 | Perimeter Drains | 80000 | 7 | 23 | 30 | 7 | 23 | 30 |  | 0 | 0 | 0 | [6 empty] | 80000
31 | ConcreteSlabs8 | Fencing | 183000 | 35 | 53 | 88 | 35 | 40 | 75 |  | 35 | 40 | 75 | 75 | 8 | 22 | 30 | 30 | 45 | 183000
32 | AshpaltSurf1 | Cement Stabilisation | 91893 | 2 | 14 | 16 | 3 | 12 | 15 |  | 3 | 12 | 15 |  | 0 | 0 | 0 |  |  | 91893 | dDiscontinue Ashpalting
33 | AshpaltSurf2 | Crushed Rock Base | 165365 | 1 | 13 | 14 | 4 | 10 | 14 |  | 4 | 10 | 14 |  | 0 | 0 | 0 |  |  | 165365
34 | AshpaltSurf3 | MC1 | 20000 | 2 | 10 | 12 | 1 | 4 | 5 |  | 1 | 4 | 5 |  | 2 | 0 | 0 |  |  | 20000
35 | AshpaltSurf4 | Colas |  | 2 | 10 | 12 | 2 | 8 | 10 |  |  | 0 | 0 |  | 0 | 0 | 0
36 | AshpaltSurf5 | Apply Ashpalt wearing course | 197000 | 7 | 20 | 27 | 4 | 8 | 12 |  | 7 | 20 | 27 | 61 | 0 | 0 | 0 | 0 |  | 197000
37 | DEMOB1 | Clean Site |  | 7 | 14 | 21 | 7 | 14 | 21 |  |  | 0 | 0 |  | 0 | 0 | 0
38 | DEMOB2 | Remove EQP/PERS from site | 293000 | 3 | 12 | 15 | 2 | 8 | 10 |  | 3 | 12 | 15 |  | 0 | 0 | 0 |  |  | 293000
39 | PreparedLoc | Prepared Location | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
40 | Durabase Mats | Transport DBM |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 3 | 6 | 9 |  |  |  | Implement Durabase Mat tech
41 | Durabase Mats | Lay DBM |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 6 | 7
42 | Durabase Mats | Retrieve DBM |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 5 | 10 | 15 | 31 | 30
Costs |  |  | 3013258
Mins
Hours
Days | [10 empty] | 84.0104 | 206 | 289.0104 |  | 45.0771 | 138.3508 | 181.4279 |  |  | 3013258
Months | [10 empty] | 3.2312 | 7.9231 | 11.1158 |  | 1.7337 | 5.3212 | 6.978
Cycle Efficiency%
Note workdays = 26days/month