## Sheet1
ProjectName | Process LT Unit | Process VAT Unit | Waste Category | Supplier | Customer | Function | Activity Decsription | Process LT | Process VAT | Process LT Minutes | Process VAT Minutes | Input | Output | Improvement | WasteCode | ActivityID
Land Location Preparation Improvement process | Day | Second | 3 | sdad | asdad | Major Projects | ISSUE PO | 14 | 12 | 6720 | 0.2 | asdad | sdad | Lean Action | M | 1
Land Location Preparation Improvement process | Day | Second | 5 | sdad | asdad | Major Projects | Contractor submit HSE, JHA plan | 21 | 5 | 10080 | 0.083334 | asdad | sdad |  | O | 2
Land Location Preparation Improvement process | Day | Second | 5 | sdad | asdad | Major Projects | Contract Owner review plan | 7 | 19 | 3360 | 0.31667 | asdad | sdad | Standard Work/Quality in Station | O | 6
Land Location Preparation Improvement process | Day | Second | 5 | sdad | asdad | Major Projects | Hold Challenge session | 7 | 21 | 3360 | 0.35 | asdad | sdad | Discontinue process | O | 7
Land Location Preparation Improvement process | Day | Second | 5 | sdad | asdad | Major Projects | Contractor Submit Equipment list | 14 | 23 | 6720 | 0.38333 | asdad | sdad | Discontinue process | O | 8
Land Location Preparation Improvement process | Minute | Second | 5 | sdad | asdad | Major Projects | Send Equip list to Logistics | 1 | 25 | 1 | 0.41667 | asdad | sdad | Standard Work/Quality in Station | O | 9
Land Location Preparation Improvement process | Day | Second | 5 | sdad | asdad | Major Projects | Inspect Equipment (Premob) | 28 | 27 | 13440 | 0.45 | asdad | sdad |  | O | 10
Land Location Preparation Improvement process | Day | Second | 5 | sdad | asdad | Major Projects | Contractor submit Security plan | 7 | 29 | 3360 | 0.48333 | asdad | sdad | Standard Work/Quality in Station/Full Delegation/Full process review | O | 11
Land Location Preparation Improvement process | Day | Second | 5 | sdad | asdad | Major Projects | Send Security plan to ASA | 0 | 31 | 0 | 0.51667 | asdad | sdad | Standard Work/Quality in Station | O | 12
Land Location Preparation Improvement process | Day | Second | 5 | sdad | asdad | Major Projects | Approve Security plan | 21 | 33 | 10080 | 0.55 | asdad | sdad |  | O | 13
Land Location Preparation Improvement process | Day | Second | 5 | sdad | asdad | Major Projects | Obtain FTO | 42 | 35 | 20160 | 0.58333 | asdad | sdad | Standard Work/Quality in Station/Full Delegation/Full process review | O | 14
Land Location Preparation Improvement process | Day | Second | 5 | sdad | asdad | Major Projects | Issue Premob Cert | 1 | 37 | 480 | 0.61667 | asdad | sdad | Standard Work/Quality in Station/Full Delegation/Full process review | O | 15
Land Location Preparation Improvement process | Day | Second | 5 | sdad | asdad | Major Projects | Contractor move EQP/PERS to site | 14 | 39 | 6720 | 0.65 | asdad | sdad |  | O | 16
Land Location Preparation Improvement process | Day | Second | 5 | sdad | asdad | Major Projects | Conduct HSE Induction | 7 | 41 | 3360 | 0.68333 | asdad | sdad |  | O | 17
Land Location Preparation Improvement process | Day | Second | 5 | sdad | asdad | Major Projects | Set up Site office | 7 | 43 | 3360 | 0.71667 | asdad | sdad |  | O | 18
Land Location Preparation Improvement process | Day | Second | 5 | sdad | asdad | Major Projects | Medical Certification | 10 | 45 | 4800 | 0.75 | asdad | sdad |  | O | 19
Land Location Preparation Improvement process | Day | Second | 5 | sdad | asdad | Major Projects | Bush Clearing | 10 | 47 | 4800 | 0.78333 | asdad | sdad |  | O | 20
Land Location Preparation Improvement process | Day | Second | 5 | sdad | asdad | Major Projects | Stripping | 7 | 49 | 3360 | 0.81667 | asdad | sdad |  | O | 21
Land Location Preparation Improvement process | Day | Second | 5 | sdad | asdad | Major Projects | SandFilling | 25 | 51 | 12000 | 0.85 | asdad | sdad |  | O | 22
Land Location Preparation Improvement process | Day | Second | 1 | sdad | asdad | Major Projects | Waste Pit | 51 | 53 | 24480 | 0.88334 | asdad | sdad | Source sand from proximate locations | T | 23
Land Location Preparation Improvement process | Day | Second | 1 | sdad | asdad | Major Projects | Cement Slab | 18 | 55 | 8640 | 0.91667 | asdad | sdad | Evaluate precast concrete/Form work Eliminate waste pit - to calculate cost benefit Elimnate or reduce Generator Slab Re-evaluate slabs from DPR regulation of containments and avoiding seepage | T | 24
Land Location Preparation Improvement process | Day | Second | 1 | sdad | asdad | Major Projects | Gen Slab | 34 | 57 | 16320 | 0.95 | asdad | sdad |  | T | 25
Land Location Preparation Improvement process | Day | Second | 1 | sdad | asdad | Major Projects | Mud Tank | 66 | 59 | 31680 | 0.98334 | asdad | sdad |  | T | 26
Land Location Preparation Improvement process | Day | Second | 1 | sdad | asdad | Major Projects | Evacuation Pit | 12 | 61 | 5760 | 1.0167 | asdad | sdad |  | T | 27
Land Location Preparation Improvement process | Day | Second | 1 | sdad | asdad | Major Projects | Cellat Pit/Slab | 72 | 63 | 34560 | 1.05 | asdad | sdad |  | T | 28
Land Location Preparation Improvement process | Day | Second | 1 | sdad | asdad | Major Projects | Flowline trench | 36 | 65 | 17280 | 1.0833 | asdad | sdad |  | T | 29
Land Location Preparation Improvement process | Day | Second | 1 | sdad | asdad | Major Projects | Perimeter Drains | 23 | 67 | 11040 | 1.1167 | asdad | sdad |  | T | 30
Land Location Preparation Improvement process | Day | Second | 1 | sdad | asdad | Major Projects | Fencing | 53 | 69 | 25440 | 1.15 | asdad | sdad |  | T | 31
Land Location Preparation Improvement process | Day | Second | 1 | sdad | asdad | Major Projects | Cement Stabilisation | 14 | 71 | 6720 | 1.1833 | asdad | sdad |  | T | 32
Land Location Preparation Improvement process | Day | Second | 1 | sdad | asdad | Major Projects | Crushed Rock Base | 13 | 73 | 6240 | 1.2167 | asdad | sdad | Implement Durabase Mat tech | T | 33
Land Location Preparation Improvement process | Day | Second | 1 | sdad | asdad | Major Projects | MC1 | 10 | 75 | 4800 | 1.25 | asdad | sdad |  | T | 34
Land Location Preparation Improvement process | Day | Second | 1 | sdad | asdad | Major Projects | Colas | 10 | 77 | 4800 | 1.2833 | asdad | sdad |  | T | 35
Land Location Preparation Improvement process | Day | Second | 1 | sdad | asdad | Major Projects | Apply Ashpalt wearing course | 20 | 79 | 9600 | 1.3167 | asdad | sdad |  | T | 36
Land Location Preparation Improvement process | Hour | Second | 1 | sdad | asdad | Major Projects | Clean Site | 14 | 81 | 840 | 1.35 | asdad | sdad |  | T | 37
Land Location Preparation Improvement process | Day | Second | 1 | sdad | asdad | Major Projects | Remove EQP/PERS from site | 12 | 83 | 5760 | 1.3833 | asdad | sdad |  | T | 38
Land Location Preparation Improvement process | Day | Second | 1 | sdad | asdad | Major Projects | Prepared Location | 10 | 85 | 4800 | 1.4167 | asdad | sdad |  | T | 39
Land Location Preparation Improvement process | Day | Second | 5 | sdad | asdad | Major Projects | Proj Eng review HSE plan | 3 | 16 | 1440 | 0.26667 | asdad | sdad | Standard Work/Quality in Station | O | 3
Land Location Preparation Improvement process | Day | Second | 5 | sdad | asdad | Major Projects | HSE Adv review HSE plan | 3 | 15 | 1440 | 0.25 | asdad | sdad | Activity | O | 4
Land Location Preparation Improvement process | Day | Second | 5 | sdad | asdad | Major Projects | Contract Holder review plan | 4 | 17 | 1920 | 0.28333 | asdad | sdad | Standard Work/Quality in Station | O | 5