## Sheet1
Project Name | Recommendation | Function | Action Function | Action Party | Target Date | CycleTime | CostReduction | Barrels | Numbers | Sponsor Comments | Champion Comments | Implementation Status | General Comments | Benefit
Pipeline Repair Process Improvement | Review existing contractor documentation process and advise actions for improvement | Production | Production | Ujah/Aisabokhale | Q4, 2014 | 3 | 0 | 0 | 0 | Approved | Approved
Pipeline Repair Process Improvement | Collate all required documents & review for standardization & integration | Production | Production | Chikere/Aisabokhale/ Ujah/Erewa/Bisiriyu/ Greg | Q4, 2014 |  | 0 | 0 | 0 | Approved | Approved
Pipeline Repair Process Improvement | F2F approval and delegation of authority | Production | Production | Jurgen | 30/9/2014 |  | 0 | 0 | 0 | Approved | Approved
Pipeline Repair Process Improvement | Engage all stakeholders for reasons of non-inclusion of GETIM option in GLMS | Production | Production | Mogbolu/Oludi | 30/9/2014 | 2 | 0 | 0 | 0 | Approved | Approved
Pipeline Repair Process Improvement | Do trend analysis to find out how much request received for specific equipment | Production | Production | Mogbolu | 30/9/2014 |  | 0 | 0 | 0 | Approved | Approved
Pipeline Repair Process Improvement | Conduct a deep dive on the option for procuring serviceable equipment | Production | Production | Agans/Jurgen | 31/12/2014 | 2 | 0 | 0 | 0 | Approved | Approved
Pipeline Repair Process Improvement | Secure dedicated GSA for SPDC swamp emergency operation | Production | Production | Jurgen/Agans | 30/09/2014 |  | 0 | 0 | 0 | Approved | Approved
Pipeline Repair Process Improvement | Expedite cash payment for GSA services through Emergency Response Team | Production | Production | Akinnawonu/Erewa/ Chuka Njoku/Amos Gagar | 30/09/2014 |  | 0 | 0 | 0 | Approved | Approved
Pipeline Repair Process Improvement | Notify GSAs of poor equipment maintenance | Production | Production | Agans/Menuchim Opara | 30/09/2014 |  | 0 | 0 | 0 | Approved | Approved
Pipeline Repair Process Improvement | Expedite cash payment for GSA services through Emergency Response Team | Production | Production | Akinnawonu/Erewa/ Chuka Njoku/Amos Gagar | 30/09/2014 |  | 0 | 0 | 0 | Approved | Approved
Pipeline Repair Process Improvement | Effect prompt payment to contractors | Production | Production | Jan Van Bunnik/Jurgen/Greg Kuwlaski | Continuous | 5 | 0 | 0 | 0 | Approved | Approved
Pipeline Repair Process Improvement | Integrate/optimize company owned equipment (e.g. OSRT boats, flat bottom boats etc.) for OSRT/ Maintenance/Operations Teams | Production | Production | Iyare/Bisiriyu working with contractors | Continuous |  | 0 | 0 | 0 | Approved | Approved
Pipeline Repair Process Improvement | Review equipment rates in line with current prevailing market realities & increase number of reliable contractors when renewing the contract | Production | Production | Tony Aisabokhale/Akinnawonu/Lambo/Udu | 31/01/2015 |  | 0 | 0 | 0 | Approved | Approved