## Sheet1
Project Name | Recommendation | Function | Action Function | Action Party | Target Date | CycleTime | CostReduction | Barrels | Numbers | Sponsor Comments | Champion Comments | Implementation Status | General Comments | Benefit
Pipeline Repair Process Improvement | Review existing contractor documentation process and advise actions for improvement | Production | Production | Production | 2014-12-30 | 3 | 0 | 0 | 0 | Approved | Approved | Ongoing | None | 0
Pipeline Repair Process Improvement | Collate all required documents & review for standardization & integration | Production | Production | Production | 2014-12-30 | 0 | 0 | 0 | 0 | Approved | Approved | Ongoing | None | 0
Pipeline Repair Process Improvement | F2F approval and delegation of authority | Production | Production | Production | 2014-09-30 | 0 | 0 | 0 | 0 | Approved | Approved | Ongoing | None | 0
Pipeline Repair Process Improvement | Engage all stakeholders for reasons of non-inclusion of GETIM option in GLMS | Production | Production | Production | 2014-09-30 | 2 | 0 | 0 | 0 | Approved | Approved | Ongoing | None | 0
Pipeline Repair Process Improvement | Do trend analysis to find out how much request received for specific equipment | Production | Production | Production | 2014-09-30 | 0 | 0 | 0 | 0 | Approved | Approved | Ongoing | None | 0
Pipeline Repair Process Improvement | Conduct a deep dive on the option for procuring serviceable equipment | Production | Production | Production | 2014-12-31 | 2 | 0 | 0 | 0 | Approved | Approved | Ongoing | None | 0
Pipeline Repair Process Improvement | Secure dedicated GSA for SPDC swamp emergency operation | Production | Production | Production | 2014-09-30 | 0 | 0 | 0 | 0 | Approved | Approved | Ongoing | None | 0
Pipeline Repair Process Improvement | Expedite cash payment for GSA services through Emergency Response Team | Production | Production | Production | 2014-09-30 | 0 | 0 | 0 | 0 | Approved | Approved | Ongoing | None | 0
Pipeline Repair Process Improvement | Notify GSAs of poor equipment maintenance | Production | Production | Production | 2014-09-30 | 0 | 0 | 0 | 0 | Approved | Approved | Ongoing | None | 0
Pipeline Repair Process Improvement | Expedite cash payment for GSA services through Emergency Response Team | Production | Production | Production | 2014-09-30 | 0 | 0 | 0 | 0 | Approved | Approved | Ongoing | None | 0
Pipeline Repair Process Improvement | Effect prompt payment to contractors | Production | Production | Production | 2015-01-30 | 5 | 0 | 0 | 0 | Approved | Approved | Ongoing | None | 0
Pipeline Repair Process Improvement | Integrate/optimize company owned equipment (e.g. OSRT boats, flat bottom boats etc.) for OSRT/ Maintenance/Operations Teams | Production | Production | Production | 2015-01-30 | 0 | 0 | 0 | 0 | Approved | Approved | Ongoing | None | 0
Pipeline Repair Process Improvement | Review equipment rates in line with current prevailing market realities & increase number of reliable contractors when renewing the contract | Production | Production | Production | 2015-01-31 | 0 | 0 | 0 | 0 | Approved | Approved | Ongoing | None | 0