## Modified Format
Project Name (must not be empty) | Function (must not be empty) | Activity Decsription (must not be empty) | Process LT (must not be empty) | Process LT Unit (must not be empty) | Process VAT (must not be empty) | Process VAT Unit (must not be empty) | Process LT Minutes (must not be empty) | Process VAT Minutes (must not be empty) | Supplier (can be empty) | Input(can be empty) | Customer(can be empty) | Output(can be empty) | Lean Tool(can be empty) | Waste Category(can be empty) | WasteCode(can be empty)
Change Management for New Initiatives | Production | ISSUE PO | 14 | Day | 12 | Second | 6720 | 0.2
Change Management for New Initiatives | Production | Contractor submit HSE, JHA plan | 21 | Day | 5 | Second | 10080 | 0.083334
Change Management for New Initiatives | Production | Contract Owner review plan | 7 | Day | 19 | Second | 3360 | 0.31667
Change Management for New Initiatives | Production | Hold Challenge session | 7 | Day | 21 | Second | 3360 | 0.35
Change Management for New Initiatives | Production | Contractor Submit Equipment list | 14 | Day | 23 | Second | 6720 | 0.38333
Change Management for New Initiatives | Production | Send Equip list to Logistics | 1 | Minute | 25 | Second | 1 | 0.41667
Change Management for New Initiatives | Production | Inspect Equipment (Premob) | 28 | Day | 27 | Second | 13440 | 0.45
Change Management for New Initiatives | Production | Contractor submit Security plan | 7 | Day | 29 | Second | 3360 | 0.48333
Change Management for New Initiatives | Production | Send Security plan to ASA | 0 | Day | 31 | Second | 0 | 0.51667
Change Management for New Initiatives | Production | Approve Security plan | 21 | Day | 33 | Second | 10080 | 0.55
Change Management for New Initiatives | Production | Obtain FTO | 42 | Day | 35 | Second | 20160 | 0.58333
Change Management for New Initiatives | Production | Issue Premob Cert | 1 | Day | 37 | Second | 480 | 0.61667
Change Management for New Initiatives | Production | Contractor move EQP/PERS to site | 14 | Day | 39 | Second | 6720 | 0.65
Change Management for New Initiatives | Production | Conduct HSE Induction | 7 | Day | 41 | Second | 3360 | 0.68333
Change Management for New Initiatives | Production | Set up Site office | 7 | Day | 43 | Second | 3360 | 0.71667
Change Management for New Initiatives | Production | Medical Certification | 10 | Day | 45 | Second | 4800 | 0.75
Change Management for New Initiatives | Production | Bush Clearing | 10 | Day | 47 | Second | 4800 | 0.78333
Change Management for New Initiatives | Production | Stripping | 7 | Day | 49 | Second | 3360 | 0.81667
Change Management for New Initiatives | Production | SandFilling | 25 | Day | 51 | Second | 12000 | 0.85
Change Management for New Initiatives | Production | Waste Pit | 51 | Day | 53 | Second | 24480 | 0.88334
Change Management for New Initiatives | Production | Cement Slab | 18 | Day | 55 | Second | 8640 | 0.91667
Change Management for New Initiatives | Production | Gen Slab | 34 | Day | 57 | Second | 16320 | 0.95
Change Management for New Initiatives | Production | Mud Tank | 66 | Day | 59 | Second | 31680 | 0.98334
Change Management for New Initiatives | Production | Evacuation Pit | 12 | Day | 61 | Second | 5760 | 1.0167
Change Management for New Initiatives | Production | Cellat Pit/Slab | 72 | Day | 63 | Second | 34560 | 1.05
Change Management for New Initiatives | Production | Flowline trench | 36 | Day | 65 | Second | 17280 | 1.0833
Change Management for New Initiatives | Production | Perimeter Drains | 23 | Day | 67 | Second | 11040 | 1.1167
Change Management for New Initiatives | Production | Fencing | 53 | Day | 69 | Second | 25440 | 1.15
Change Management for New Initiatives | Production | Cement Stabilisation | 14 | Day | 71 | Second | 6720 | 1.1833
Change Management for New Initiatives | Production | Crushed Rock Base | 13 | Day | 73 | Second | 6240 | 1.2167
Change Management for New Initiatives | Production | MC1 | 10 | Day | 75 | Second | 4800 | 1.25
Change Management for New Initiatives | Production | Colas | 10 | Day | 77 | Second | 4800 | 1.2833
Change Management for New Initiatives | Production | Apply Ashpalt wearing course | 20 | Day | 79 | Second | 9600 | 1.3167
Change Management for New Initiatives | Production | Clean Site | 14 | Hour | 81 | Second | 840 | 1.35
Change Management for New Initiatives | Production | Remove EQP/PERS from site | 12 | Day | 83 | Second | 5760 | 1.3833
Change Management for New Initiatives | Production | Prepared Location | 10 | Day | 85 | Second | 4800 | 1.4167
Change Management for New Initiatives | Production | Proj Eng review HSE plan | 3 | Day | 16 | Second | 1440 | 0.26667
Change Management for New Initiatives | Production | HSE Adv review HSE plan | 3 | Day | 15 | Second | 1440 | 0.25
Change Management for New Initiatives | Production | Contract Holder review plan | 4 | Day | 17 | Second | 1920 | 0.28333